## Fix and bugs
No | Bug | Details | Expected result | Fix
1 | WP7 - Draft attachment binary was not persisted reliably | The custom draft attachment flow initially stored metadata but did not always preserve binary content across activation/restart. | Attachment metadata and binary content remain available after activation and local CAP restart. | Fixed by aligning the stream persistence path with the CAP draft-root flow and verifying create/upload/activate/download/history. | Sprint 02 evidence
2 | WP5/WP7 - Comments and history exposed technical identifiers | Comments, history, and notifications previously exposed raw IDs or unreadable audit detail instead of business-friendly names. | Sub-tables show readable names, labels, and remain read-only for normal usage. | Fixed through service projection enrichment, text annotations, and read-only hardening. | Sprint 02 evidence
3 | WP4 - Assign Developer action parameter still shows UUID after selection | The Fiori Elements action parameter dialog still renders the selected assignee parameter as a raw UUID after value-help selection. | The dialog should display business text or a friendlier parameter input for mentor-facing UX. | Open item. Current workaround is business-friendly value-help rows plus correct Object Page display after action execution. Future fix: targeted FE/UI5 extension. | Sprint 02 evidence
4 | WP4/WP5 - Comments section lacks a local Add Comment entry point | Comment creation is currently discoverable from the page header action but not from the Comments section itself. | Users should be able to add comments from the conversation context. | Open UX backlog item. Candidate solution: section-level action or targeted FE/UI5 extension after core happy flows are stable. | Sprint 02 evidence
6