## Fix and bugs
No | Defect / ownership | Reproduction / actual | Expected / traceability | Root cause / fix / retest | Evidence v0.5 — 2026-07-23T10:59:20+07:00
1 | IDTS-13 — Object Page stale after lifecycle action ¦ Classification: Product defect ¦ Severity / priority / status: High / High / Closed ¦ Reporter / owner: IDTS team / DatDT / DonHV ¦ Discovered / closed: 2026-06-27 / 2026-06-28 | Preconditions: Open Object Page for an actionable bug. ¦ Steps to reproduce: Run a lifecycle action and observe stale bound data. ¦ Actual result: Bound data stayed stale. ¦ Environment / build: Fiori Elements OData V4 | Expected result: Status, ownership and related sections refresh. ¦ Requirement IDs: SRS-FR-STATUS-008 ¦ Related test case IDs: FT-LIFECYCLE-001 | Root cause: Side effects targeted properties instead of the bound entity. ¦ Fix description: Use TargetEntities [$self]. ¦ Retest command / steps: Browser lifecycle UAT plus CAP compile ¦ Retest result / date: Passed in historical browser UAT; fresh full lifecycle remains NOT_RUN in this remediation. / 2026-06-28 ¦ Remaining action: Run FT-LIFECYCLE-001 for current mentor evidence. | docs/pm/status/datdt.md
2 | IDTS-19 — History Timeline fails when text exists ¦ Classification: Product defect ¦ Severity / priority / status: High / High / Closed ¦ Reporter / owner: IDTS team / SangVN / DonHV ¦ Discovered / closed: 2026-06-28 / 2026-06-28 | Preconditions: History event contains text. ¦ Steps to reproduce: Open a bug with textual history in the custom timeline. ¦ Actual result: UI5 FormatException occurred. ¦ Environment / build: SAPUI5 Object Page | Expected result: Readable timeline renders. ¦ Requirement IDs: SRS-FR-AUDIT-001 ¦ Related test case IDs: FT-REASSIGN-001, FT-DEV-INFO-001 | Root cause: Invalid nested expression binding. ¦ Fix description: Replaced invalid expression and retested timeline. ¦ Retest command / steps: Browser history UAT ¦ Retest result / date: Passed historically. / 2026-06-28 ¦ Remaining action: Capture fresh UAT evidence when executed. | docs/pm/status/sangvn.md
3 | IDTS-32 — Invalid catalog values accepted ¦ Classification: Product defect ¦ Severity / priority / status: High / High / Closed ¦ Reporter / owner: IDTS QA / DonHV ¦ Discovered / closed: 2026-06-29 / 2026-07-23 | Preconditions: Authorized create/update request. ¦ Steps to reproduce: Submit numeric-like, unknown, blank or inactive priority/severity/environment values. ¦ Actual result: Invalid values could be accepted before the fix. ¦ Environment / build: CAP service | Expected result: Backend rejects invalid values and preserves state. ¦ Requirement IDs: SRS-FR-BUG-002, SRS-FR-CLASS-003 ¦ Related test case IDs: FT-VALID-001, FT-CREATE-001 | Root cause: Catalog activity/format validation was incomplete. ¦ Fix description: Added target, active-code and draft validation. ¦ Retest command / steps: npm run qa:idts41:programmatic ¦ Retest result / date: 18 passed, 0 failed. / 2026-07-23 ¦ Remaining action: UI UAT remains prepared. | scripts/qa/test-idts41-code-list-validation.js
4 | IDTS-35 — Blank app after successful login ¦ Classification: Product defect ¦ Severity / priority / status: Critical / High / Closed ¦ Reporter / owner: DatDT / DatDT ¦ Discovered / closed: 2026-06-30 / 2026-06-30 | Preconditions: Valid user credentials. ¦ Steps to reproduce: Log in, then load the protected Fiori app. ¦ Actual result: Metadata request preceded the interceptor and returned 401. ¦ Environment / build: SAPUI5 + custom CAP auth | Expected result: Metadata loads with bearer token and the app renders. ¦ Requirement IDs: SRS-FR-AUTH-001, SRS-FR-AUTH-002 ¦ Related test case IDs: FT-AUTH-SESSION-001 | Root cause: Bearer interceptor installed after UI5 OData startup. ¦ Fix description: Install auth guard/interceptor before UI5 bootstrap. ¦ Retest command / steps: npm run qa:auth:programmatic ¦ Retest result / date: 28 passed, 0 failed for backend auth; current browser login UAT not rerun. / 2026-07-23 ¦ Remaining action: Fresh browser UAT if required by mentor. | docs/pm/status/datdt.md
5 | IDTS-41 — Developer can start unauthorized root draft ¦ Classification: Product defect ¦ Severity / priority / status: High / High / Closed ¦ Reporter / owner: IDTS QA / DonHV ¦ Discovered / closed: 2026-06-29 / 2026-07-23 | Preconditions: Authenticated Developer. ¦ Steps to reproduce: Call root draft NEW as Developer. ¦ Actual result: Draft creation was not blocked before the fix. ¦ Environment / build: CAP draft service | Expected result: 403 and no draft. ¦ Requirement IDs: SRS-FR-AUTH-002, SRS-FR-BUG-001 ¦ Related test case IDs: FT-AUTHZ-001 | Root cause: Authorization was missing at root draft NEW. ¦ Fix description: Added backend role check before draft creation. ¦ Retest command / steps: npm run qa:idts41:programmatic ¦ Retest result / date: Developer denied; Tester and PM allowed. / 2026-07-23 ¦ Remaining action: Fresh UI action-visibility UAT. | scripts/qa/test-idts41-code-list-validation.js
6 | IDTS-49 — Draft activation rejects missing reporter ¦ Classification: Product defect ¦ Severity / priority / status: High / High / Closed ¦ Reporter / owner: IDTS QA / DonHV ¦ Discovered / closed: 2026-07-02 / 2026-07-02 | Preconditions: PM/Tester creates a root draft. ¦ Steps to reproduce: Activate an authorized draft without client-supplied reporter. ¦ Actual result: Required-field validation ran before derivation. ¦ Environment / build: CAP draft service | Expected result: Backend derives reporter before validation. ¦ Requirement IDs: SRS-FR-BUG-001 ¦ Related test case IDs: FT-CREATE-001 | Root cause: Reporter derived too late in active CREATE. ¦ Fix description: Initialize reporter during draft NEW/SAVE. ¦ Retest command / steps: npm run qa:draft-reporter:programmatic ¦ Retest result / date: Passed historically; not rerun in this six-suite remediation. / 2026-07-02 ¦ Remaining action: No new claim beyond historical evidence. | docs/pm/status/donhv.md
7 | IDTS-52 — UI5 login page renders blank ¦ Classification: Product defect ¦ Severity / priority / status: High / High / Closed ¦ Reporter / owner: IDTS QA / DatDT / DonHV ¦ Discovered / closed: 2026-07-03 / 2026-07-03 | Preconditions: Unauthenticated browser. ¦ Steps to reproduce: Open the custom login page on the affected build. ¦ Actual result: Undefined enum access stopped rendering. ¦ Environment / build: SAPUI5 login page | Expected result: Login controls and safe validation render. ¦ Requirement IDs: SRS-FR-AUTH-001 ¦ Related test case IDs: FT-AUTH-SESSION-001 | Root cause: Unstable UI5 enum access. ¦ Fix description: Use stable string enum values. ¦ Retest command / steps: Browser login smoke ¦ Retest result / date: Passed historically; current browser UAT not rerun. / 2026-07-03 ¦ Remaining action: Fresh browser evidence if mentor requests it. | docs/pm/status/donhv.md
8 | IDTS-53 — Profile overlay intercepts Sign Out ¦ Classification: Product defect ¦ Severity / priority / status: Medium / High / Closed ¦ Reporter / owner: IDTS QA / DatDT / DonHV ¦ Discovered / closed: 2026-07-03 / 2026-07-03 | Preconditions: Authenticated app. ¦ Steps to reproduce: Open profile popover and click Sign Out in the affected layout. ¦ Actual result: Fixed overlay intercepted pointer events. ¦ Environment / build: SAPUI5 shell | Expected result: Sign Out is clickable and revokes the session. ¦ Requirement IDs: SRS-FR-AUTH-002 ¦ Related test case IDs: FT-AUTH-SESSION-001 | Root cause: Pointer-event handling on fixed host. ¦ Fix description: Adjusted pointer events for host and button. ¦ Retest command / steps: Browser profile/logout smoke ¦ Retest result / date: Passed historically; backend logout/revocation passed fresh. / 2026-07-23 ¦ Remaining action: Fresh browser click evidence remains outside this run. | docs/pm/status/donhv.md
9 | IDTS-55 — Comments and attachments interaction defects ¦ Classification: Product defect ¦ Severity / priority / status: High / High / Closed ¦ Reporter / owner: IDTS QA / DonHV ¦ Discovered / closed: 2026-07-04 / 2026-07-04 | Preconditions: Existing bug with child sections. ¦ Steps to reproduce: Post a comment or remove an attachment from the affected Object Page fragments. ¦ Actual result: Context/refresh/root detection was incorrect. ¦ Environment / build: Fiori Object Page + CAP attachments | Expected result: Correct context, immediate refresh and safe deletion. ¦ Requirement IDs: SRS-FR-COMMENT-001, SRS-DATA-007 ¦ Related test case IDs: FT-COMMENT-001, FT-ATTACH-001 | Root cause: Lost binding context, unsupported refresh and child/root confusion. ¦ Fix description: Propagate context, use supported refresh and strict root detection. ¦ Retest command / steps: npm run qa:comments-attachments:programmatic; npm run qa:comments-attachments:http ¦ Retest result / date: Fresh comment persistence passed; attachment HTTP remains NOT_RUN. / 2026-07-23 ¦ Remaining action: Run FT-ATTACH-001 before claiming current attachment PASS. | docs/pm/status/donhv.md
10 | IDTS-56 — Smart Assign treats hidden classification as missing ¦ Classification: Product defect ¦ Severity / priority / status: High / High / Closed ¦ Reporter / owner: IDTS QA / DonHV ¦ Discovered / closed: 2026-07-05 / 2026-07-05 | Preconditions: Classified bug with sparse UI selection. ¦ Steps to reproduce: Open Smart Assign when component category was not selected in the Object Page payload. ¦ Actual result: UI reported missing context. ¦ Environment / build: Fiori Smart Assign | Expected result: Valid classification context is derived and candidates load. ¦ Requirement IDs: SRS-FR-ASSIGN-001 ¦ Related test case IDs: FT-CLASS-ASSIGN-001 | Root cause: UI depended on an internal field not always selected. ¦ Fix description: Corrected context derivation and tests. ¦ Retest command / steps: npm run qa:idts56:programmatic ¦ Retest result / date: Passed historically; fresh Smart Assign execution not part of this run. / 2026-07-05 ¦ Remaining action: Execute FT-CLASS-ASSIGN-001 for current mentor evidence. | docs/pm/status/donhv.md
11 | IDTS-58 — Profile/comment/attachment UX defects ¦ Classification: Product defect ¦ Severity / priority / status: Medium / High / Closed ¦ Reporter / owner: DatDT / DatDT ¦ Discovered / closed: 2026-07-05 / 2026-07-05 | Preconditions: Authenticated app and editable bug. ¦ Steps to reproduce: Use dashboard profile, comment feed and attachment delete while a draft exists. ¦ Actual result: Profile overlapped, author repeated, delete stayed enabled. ¦ Environment / build: SAPUI5/Fiori | Expected result: No overlap/duplicate author and delete is disabled during draft. ¦ Requirement IDs: SRS-FR-COMMENT-001, SRS-DATA-007 ¦ Related test case IDs: FT-COMMENT-001, FT-ATTACH-001 | Root cause: Header placement, feed formatting and draft-state guard defects. ¦ Fix description: Moved action, normalized feed and disabled delete during draft. ¦ Retest command / steps: Local browser smoke ¦ Retest result / date: Passed historically; attachment current execution remains NOT_RUN. / 2026-07-05 ¦ Remaining action: Current browser/UAT evidence pending. | docs/pm/status/datdt.md
12 | IDTS-78 — Standalone AI sections outside business context ¦ Classification: Product UX defect ¦ Severity / priority / status: Medium / High / Closed ¦ Reporter / owner: IDTS QA / DonHV ¦ Discovered / closed: 2026-07-11 / 2026-07-11 | Preconditions: AI review UI build before placement fix. ¦ Steps to reproduce: Open the Object Page and locate standalone AI sections. ¦ Actual result: Standalone titled sections remained visible. ¦ Environment / build: Fiori Object Page | Expected result: Review actions appear near the related business context. ¦ Requirement IDs: SRS-FR-AI-002 ¦ Related test case IDs: FT-AI-REVIEW-001, UAT-006 | Root cause: Manifest custom sections remained after placement polish. ¦ Fix description: Removed standalone sections and kept review actions inline. ¦ Retest command / steps: Deployed AI UI smoke ¦ Retest result / date: Passed historically; fresh full human-review flow remains NOT_RUN. / 2026-07-11 ¦ Remaining action: Execute FT-AI-REVIEW-001 or UAT-006 for current evidence. | docs/pm/status/donhv.md