## Fix and bugs
No | Bug | Details | Expected result | Fix
1 | IDTS-5 - SC-01a direct CAP CREATE verification failed | Merged QA harness dispatched CREATE without an INSERT query, then exposed a missing explicit UUID. | A valid bug request is created successfully and the complete backend suite passes. | Added INSERT query and explicit UUIDs; rerun result: 21/21 PASS. | WP4 / Sprint 02 evidence
2 | WP4 - Assignee value help showed technical columns and labels | Assignee picker displayed developerProfile_ID and responsibilityLevel_code; common value helps also used generic headers such as code and name. | Assignee and common value helps show business-readable labels and columns. | Added AssignableDevelopers projection, value-list annotations, and property-level labels. | WP4 / Sprint 02 evidence
3 | WP4 - Selected Assignee displayed raw UUID | After selecting a developer, the Assignee field showed the DeveloperProfile UUID instead of the user display name. | Assignee field displays the selected developer display name, for example DatDT. | Added assigneeDisplayName projection/enrichment for active and draft reads plus side-effect refresh. | WP4 / Sprint 02 evidence
4 | WP4 - Create layout was not aligned with Tester mental flow | Assignment-first layout surfaced technical assignment controls before the user had described the bug. | Create/Object Page follows General Information, Classification and Assignment, then Reproduction and Test Context. | Recorded C-prime as the target layout for the next WP4 UI refinement baseline. | WP4 / Sprint 02 evidence
6