## Summary
Field | Value
Generated At | 2026-07-24
Mode | EXECUTE
Source Of Truth | Repository Markdown + current IDTS-100 Shared QA evidence
Purpose | SAP490 mentor/team review workbook; current result: 21 PASSED cases and 6 PREPARED human UAT cases
Overwrite Behavior | Current Drive file is updated in place; repository workbook remains the source of truth; no copy or delete.

## Requirement Backlog
ID | Title | Priority | Primary Role | User Story / Summary | Acceptance Criteria | Source
REQ-BUG-001 | Create Bug Report | P0 | Tester | As a Tester, I want to create a bug report with complete defect information so that the team can track and process it. | Tester can enter title, description, priority, severity, environment, steps to reproduce, actual result, expected result, SAP Module if relevant, Application Component, Defect Category, and optional evidence/test references. Required fields are validated before submit. System creates a unique bug number/ID. System writes a create history log. | docs/ba/04-requirement-backlog.md
REQ-BUG-002 | Check Existing Bugs Before Creation | P0 | Tester | As a Tester, I want to search existing bugs before creating a new bug so that duplicates are reduced. | Tester can search/filter by title, status, priority, severity, SAP Module, Application Component, Defect Category, assignee, and keyword. If a similar open bug exists, Tester can follow/comment/update that bug instead of creating a duplicate. If a similar closed bug exists, Tester can reopen or update according to authorization. | docs/ba/04-requirement-backlog.md
REQ-CLS-001 | Classify Bug by SAP Module, Application Component, and Defect Category | P0 | Tester | As a Tester, I want classification fields to be clear and dependent so that I can describe where the bug appears and what type of defect it is. | SAP Module is optional and represents business context such as FI/MM/SD. Application Component is required. Defect Category is required. Application Component value help can be filtered by SAP Module when configured. Defect Category value help can be filtered by Application Component. Pure IDTS bugs can use empty/Not Applicable SAP Module. | docs/ba/04-requirement-backlog.md
REQ-ASSIGN-001 | Filter Developers by Responsibility | P0 | Tester | As a Tester, I want the assignee list to show suitable Developers based on selected classification so that assignment is less likely to be wrong. | System resolves the selected Application Component + Defect Category into a Component Category. System filters Developers by active Developer Responsibility. If SAP Module is selected, responsibility can be restricted by that SAP Module. If no Developer matches, Tester can choose "No suitable developer". | docs/ba/04-requirement-backlog.md
REQ-ASSIGN-002 | Submit as Assigned or Pending Assignment | P0 | Tester | As a Tester, I want to submit a bug even when no suitable Developer exists so that valid defects are not lost. | If a Developer is selected, status becomes Assigned. If "No suitable developer" is selected, status becomes Pending Assignment. Assignment decision is written to history log. Assigned Developer receives notification trigger. Pending Assignment appears in PM/Tester monitoring. | docs/ba/04-requirement-backlog.md
REQ-DEV-001 | Developer Review | P0 | Developer | As a Developer, I want to review assigned bugs so that I can decide whether I can process them. | Developer can view assigned bugs and bug details. Developer can move Assigned to In Review. Developer can add developer note/comment. Developer can request more information with reason. Developer can reject wrong classification or unsuitable assignment with reason. | docs/ba/04-requirement-backlog.md
REQ-INFO-001 | Request More Information | P0 | Developer | As a Developer, I want to request missing information so that I do not process unclear bugs. | Developer can set status to Need More Information. Reason is required. nextProcessor becomes Tester. Tester receives notification trigger. Tester can add information and return bug to Assigned/In Review. | docs/ba/04-requirement-backlog.md
REQ-REJECT-001 | Reject and Reassign | P0 | Developer, Tester, PM | As a Developer, I want to reject wrongly classified or unsuitable bugs so that the Tester can correct them. | Developer can reject with required reason. Status becomes Rejected. nextProcessor becomes Tester or PM. Rejected is not final; Tester or PM must perform the next action. Tester can update classification and reassign. Tester or PM can move the bug from Rejected to Assigned when a suitable Developer is selected. Tester or PM can move the bug from Rejected to Pending Assignment when no suitable Developer is available. Reassignment is logged as action/history, not as a separate status. Rejected không phải final status. Sau khi reject, Tester hoặc PM phải xử lý tiếp bằng cách sửa phân loại, bổ sung thông tin, reassign sang Developer phù hợp hoặc chuyển về Pending Assignment nếu chưa có Developer phù hợp. | docs/ba/04-requirement-backlog.md
REQ-STATUS-001 | Resolve, Retest, Close, and Reopen | P0 | Developer, Tester/PM | As the team, we need a controlled closure flow so that a bug is not closed before verification. | Developer can move In Progress to Resolved. Tester/System can move Resolved to Retest Required when verification is needed. Tester/PM can close when accepted. Tester/PM can reopen when the issue still exists. Closed bugs are not freely edited; Reopen is used to continue processing. | docs/ba/04-requirement-backlog.md
REQ-NEXTP-001 | Maintain Next Processor | P0 | System | As the system, I want to maintain nextProcessor automatically so that users and PM know who must act next. | nextProcessor changes based on status/action rules. nextProcessor does not replace assignee. Closed bugs have no nextProcessor. Important nextProcessor changes are logged. PM can filter/monitor by nextProcessor or inferred queue. | docs/ba/04-requirement-backlog.md
REQ-COMMENT-001 | Add Comments | P0 | Tester, Developer, PM | As a user, I want to comment on a bug so that discussions stay attached to the defect record. | Tester, assigned Developer, and PM can comment according to authorization. Comment stores content, author, author role, timestamp, and bug reference. Comment does not directly change status. | docs/ba/04-requirement-backlog.md
REQ-HISTORY-001 | Audit and History Log | P0 | System | As the system, I want to log important changes so that defect handling is traceable. | Log create, edit, assign, reassign, status change, request more information, reject, resolve, retest, close, reopen, attachment, and key notification events. History records actor, role, timestamp, action type, old value, new value, and reason when available. | docs/ba/04-requirement-backlog.md
REQ-PM-001 | PM Monitoring | P0 | PM | As a PM, I want to monitor workload, overdue bugs, pending assignment, and status progress so that I can manage delivery risk. | PM can see all bugs. PM can filter by status, priority, severity, SAP Module, Application Component, Defect Category, assignee, nextProcessor, created date, updated date, and overdue state. PM can see workload by Developer. PM can see Pending Assignment and overdue bugs. PM can comment or request reassignment without replacing Developer responsibilities. | docs/ba/04-requirement-backlog.md
REQ-ATT-001 | Attachment metadata | P1 |  | Store file name, media type, storage reference, uploader, and timestamp. |  | docs/ba/04-requirement-backlog.md
REQ-NOTIF-001 | Notification records | P1 |  | Store notification event, recipient, channel, delivery status, and timestamp. |  | docs/ba/04-requirement-backlog.md
REQ-WORKLOAD-001 | Workload warning | P1 |  | Warn Tester/PM when Developer is overloaded. |  | docs/ba/04-requirement-backlog.md
REQ-DUP-001 | Duplicate links | P1 |  | Record source/target bug duplicate relationships. |  | docs/ba/04-requirement-backlog.md
REQ-VALUE-001 | Managed value lists | P1 |  | Use controlled values for priority, severity, status, SAP Module, Application Component, and Defect Category. |  | docs/ba/04-requirement-backlog.md
REQ-NOTIF-002 | External notification adapter | P2 |  | Add email/SAP BTP/third-party delivery later without hardcoding endpoints. |  | docs/ba/04-requirement-backlog.md
REQ-REPORT-001 | Advanced analytics | P2 |  | Add trend charts and SLA analytics after MVP. |  | docs/ba/04-requirement-backlog.md
REQ-WATCH-001 | Watchers/collaborators | P2 |  | Allow non-assignee users to follow a bug. |  | docs/ba/04-requirement-backlog.md

## Traceability Matrix
Source | Section | Column 1 | Column 2 | Column 3 | Column 4 | Column 5
docs/ba/brd/brd.en.md | 23. Traceability Matrix | Digitize defect reporting | Bug Reporting | BRD-BR-001 | BR-RULE-001 | Bug can be created with required information.
docs/ba/brd/brd.en.md | 23. Traceability Matrix | Reduce duplicate defects | Duplicate Support | BRD-BR-002 | BR-RULE-002 | Duplicate search/filter support exists before creation.
docs/ba/brd/brd.en.md | 23. Traceability Matrix | Improve classification quality | Classification | BRD-BR-003 | BR-RULE-003, BR-RULE-004 | Required classification fields are captured.
docs/ba/brd/brd.en.md | 23. Traceability Matrix | Improve assignment accuracy | Developer Matching | BRD-BR-004 | BR-RULE-005, BR-RULE-006 | Developer candidates are filtered by responsibility.
docs/ba/brd/brd.en.md | 23. Traceability Matrix | Avoid unowned valid bugs | Assignment | BRD-BR-005 | BR-RULE-007 | Pending Assignment queue exists.
docs/ba/brd/brd.en.md | 23. Traceability Matrix | Control developer review | Developer Review | BRD-BR-006, BRD-BR-007 | BR-RULE-008, BR-RULE-009 | Developer can request information or reject with reason.
docs/ba/brd/brd.en.md | 23. Traceability Matrix | Control lifecycle | Retest and Closure | BRD-BR-009 | BR-RULE-010, BR-RULE-011 | Bugs follow allowed lifecycle states.
docs/ba/brd/brd.en.md | 23. Traceability Matrix | Preserve collaboration | Comments | BRD-BR-010 | BR-RULE-012 | Comments do not silently change status.
docs/ba/brd/brd.en.md | 23. Traceability Matrix | Preserve auditability | History Log | BRD-BR-011 | BR-RULE-013 | Important actions are recorded in history.
docs/ba/brd/brd.en.md | 23. Traceability Matrix | Improve PM visibility | PM Monitoring | BRD-BR-013 | BR-RULE-014 | PM can monitor workload, queues, overdue bugs, and follow-up.
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-001 Structured bug reporting | SRS-FR-BUG-001, SRS-FR-BUG-002, SRS-DATA-001, SRS-DATA-002 | FRS-BUG-001
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-002 Duplicate checking | SRS-FR-BUG-003, SRS-FR-BUG-004 | FRS-BUG-002
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-003 Classification | SRS-FR-CLASS-001 to SRS-FR-CLASS-005, SRS-DATA-004 | FRS-CLASS-001, FRS-UX-001
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-004 Developer assignment | SRS-FR-ASSIGN-001, SRS-FR-ASSIGN-002, SRS-DATA-005 | FRS-ASSIGN-001
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-005 Pending Assignment | SRS-FR-ASSIGN-003, SRS-FR-PM-003 | FRS-ASSIGN-002
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-006 Developer review | SRS-FR-STATUS-001, SRS-FR-STATUS-002, SRS-FR-STATUS-005 | FRS-DEV-001, FRS-INFO-001
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-007 Controlled rejection | SRS-FR-STATUS-003, SRS-FR-STATUS-004 | FRS-REJECT-001
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-008 Rejected follow-up | SRS-FR-STATUS-003, SRS-FR-STATUS-004, SRS-FR-STATUS-009 | FRS-REJECT-001, FRS-NEXTP-001
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-009 Status lifecycle | SRS-FR-STATUS-006 to SRS-FR-STATUS-008 | FRS-STATUS-002 to FRS-STATUS-005
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-010 Comments | SRS-FR-COMMENT-001, SRS-FR-COMMENT-002 | FRS-COMMENT-001
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-011 History log | SRS-FR-AUDIT-001, SRS-FR-AUDIT-002 | FRS-AUDIT-001
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-012 Notification records | SRS-FR-NOTIF-001, SRS-FR-NOTIF-002 | FRS-NOTIF-001
docs/ba/srs/srs.en.md | 11. Traceability Matrix | BRD-BR-013 PM monitoring | SRS-FR-PM-001 to SRS-FR-PM-004 | FRS-PM-001, FRS-PM-002
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-BUG-001 | SRS-FR-BUG-001, SRS-FR-BUG-002, SRS-DATA-001, SRS-DATA-002
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-BUG-002 | SRS-FR-BUG-003, SRS-FR-BUG-004
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-CLASS-001 | SRS-FR-CLASS-001 to SRS-FR-CLASS-005
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-ASSIGN-001 | SRS-FR-ASSIGN-001, SRS-FR-ASSIGN-002
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-ASSIGN-002 | SRS-FR-ASSIGN-003, SRS-FR-PM-003
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-ASSIGN-003 | SRS-FR-ASSIGN-004, SRS-FR-STATUS-004
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-DEV-001 | SRS-FR-STATUS-001, SRS-FR-STATUS-005
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-INFO-001 | SRS-FR-STATUS-002, SRS-FR-STATUS-009
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-REJECT-001 | SRS-FR-STATUS-003, SRS-FR-STATUS-004, SRS-FR-STATUS-009
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-STATUS-002 | SRS-FR-STATUS-006, SRS-FR-STATUS-007
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-STATUS-003 | SRS-FR-BUG-005, SRS-FR-STATUS-007
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-STATUS-005 | SRS-FR-STATUS-008, SRS-NFR-INT-001
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-NEXTP-001 | SRS-FR-STATUS-009
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-COMMENT-001 | SRS-FR-COMMENT-001, SRS-FR-COMMENT-002
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-AUDIT-001 | SRS-FR-AUDIT-001, SRS-FR-AUDIT-002
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-NOTIF-001 | SRS-FR-NOTIF-001, SRS-FR-NOTIF-002
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-PM-001 | SRS-FR-PM-001, SRS-FR-PM-002, SRS-FR-PM-003
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-PM-002 | SRS-FR-PM-004
docs/ba/frs/frs.en.md | 8. Traceability to SRS | FRS-UX-001 | SRS-IF-UI-001 to SRS-IF-UI-005, SRS-NFR-USE-001, SRS-NFR-USE-002

## Business Rule Matrix
Rule ID | Rule Title | Rule Group | Summary | Source
BR-01 | Tester có quyền ghi nhận bug | A. Business Rules về Role và quyền hạn | Tester được phép: Detect bug Check existing bug Create bug report Add bug description Set priority, severity, module/category Upload screenshot/evidence Submit bug report Edit submitted bug report Assign bug cho Developer Reassign bug cho Developer khác Add comment/feedback Track bug status Trong MVP hiện tại, Reporter không tách thành role riêng vì Tester là người chính phát hiện và báo cáo bug nội bộ. Admin cũng chưa tách thành role riêng vì chưa có workflow admin chuyên biệt; các trách nhiệm quản trị nhẹ như sửa phân loại, duy trì master data hoặc điều phối reassignment sẽ do Tester hoặc PM xử lý theo quyền được cấp. | IDTS-Business-Rule.md
BR-02 | Developer chỉ xử lý bug được assign hoặc bug có quyền xem | A. Business Rules về Role và quyền hạn | Developer được phép: View assigned bugs View bug details Review bug information Request more information Add developer note Update bug status Reject assigned bug nếu bug sai module hoặc thông tin không phù hợp; phải có lý do reject và follow-up owner Comment trong bug report Developer không phải người tạo bug chính và không trực tiếp sửa code trong hệ thống. | IDTS-Business-Rule.md
BR-03 | PM có quyền giám sát, không trực tiếp xử lý bug | A. Business Rules về Role và quyền hạn | PM được phép: View all bug reports View bug details Search/filter bugs Track bug status View bug history Monitor developer workload View overdue bugs View dashboard/report Receive escalation notification Request reassignment when needed PM không phải người trực tiếp tạo bug, fix bug hoặc cập nhật technical note thay Developer. | IDTS-Business-Rule.md
BR-04 | Tester phải kiểm tra bug đã tồn tại trước khi tạo bug mới | B. Business Rules về tạo và ghi nhận bug | Trước khi tạo bug mới, Tester cần kiểm tra trong hệ thống xem bug tương tự đã tồn tại chưa. Mục tiêu là giảm bug trùng lặp và giữ dữ liệu bug sạch hơn. | IDTS-Business-Rule.md
BR-05 | Bug report phải có thông tin bắt buộc trước khi submit | B. Business Rules về tạo và ghi nhận bug | Một bug report chỉ được phép gửi khi tất cả thông tin bắt buộc đã được điền đầy đủ. Nếu thiếu bất kỳ field bắt buộc nào, hệ thống phải chặn việc submit và hiển thị thông báo lỗi cho Tester. Các field nên bắt buộc gồm: Các field có thể để không bắt buộc: Với field Environment, nếu muốn hệ thống rõ hơn thì nên bắt buộc, ví dụ: Trình duyệt Thiết bị Hệ điều hành Môi trường test SAP system/client nếu có | IDTS-Business-Rule.md
BR-06 | Screenshot/evidence là thông tin hỗ trợ, không luôn bắt buộc | B. Business Rules về tạo và ghi nhận bug | Tester có thể upload: Screenshot Log file Video ngắn Error message Other evidence Tuy nhiên, evidence có thể là optional, trừ khi nhóm quy định một số loại bug bắt buộc phải có bằng chứng. Ví dụ: | IDTS-Business-Rule.md
BR-07 | Bug phải được phân loại theo module/category | B. Business Rules về tạo và ghi nhận bug | Khi tạo bug, Tester cần chọn module/category liên quan. Ví dụ: Login User Management Defect Management Notification Workflow Dashboard SAP Integration Module/category được dùng để hỗ trợ việc assign Developer phù hợp. | IDTS-Business-Rule.md
BR-08 | Tester có quyền assign bug cho Developer | C. Business Rules về assign và reassign bug | Sau khi submit bug report, Tester có thể assign bug cho Developer xử lý. Luồng nghiệp vụ: Tester creates bug report → Tester selects module/category → System lists Developers by selected module → Tester assigns bug to a Developer | IDTS-Business-Rule.md
BR-09 | Danh sách Developer nên được lọc theo module/category | C. Business Rules về assign và reassign bug | Sau khi Tester chọn module/category, hệ thống chỉ nên hiển thị Developer phù hợp với module đó. Ví dụ: Rule này giúp giảm việc assign sai Developer. | IDTS-Business-Rule.md
BR-10 | Hệ thống hoặc Tester cần kiểm tra workload/availability trước khi assign | C. Business Rules về assign và reassign bug | Trước khi bug được assign chính thức, cần kiểm tra Developer có phù hợp không. Nếu nhóm chưa làm tự động workload, có thể để việc kiểm tra này ở mức thủ công. | IDTS-Business-Rule.md
BR-11 | Tester có thể reassign bug sang Developer khác | C. Business Rules về assign và reassign bug | Tester có thể reassign bug trong các trường hợp: Developer đang bận Workload không phù hợp Developer reject bug và cần follow-up/reassign Bug bị phân sai module PM yêu cầu reassign Developer không cập nhật trong thời gian dài Khi reassign, hệ thống nên lưu lại lịch sử: Bug từng được assign cho ai Ai thực hiện reassign Lý do reassign Thời gian reassign | IDTS-Business-Rule.md
BR-12 | Developer có thể reject assigned bug nếu bug không phù hợp | C. Business Rules về assign và reassign bug | Developer được phép reject bug nếu: Bug không thuộc module Developer phụ trách Bug bị phân loại sai category Bug description không liên quan đến phạm vi xử lý Bug cần chuyển sang Developer khác Sau khi Developer reject, status của bug có thể là Rejected, nhưng Rejected không được xem là trạng thái kết thúc. Hệ thống bắt buộc phải: Lưu rejection reason Ghi history log Set nextProcessor là Tester hoặc PM Xác định action follow-up tiếp theo Sau khi Developer reject, Tester hoặc PM phải follow up để: Update module/category Bổ sung thông tin Reassign cho Developer khác Hoặc đưa bug về Pending Assignment nếu chưa có Developer phù hợp English clarification: Rejected is a follow-up status, not a final status. Every rejected bug must have a reason, a next processor, and a clear next action such as reclassification, additional information, reassignment, or Pending Assignment. Giải thích tiếng Việt: Rejected là trạng thái cần xử lý tiếp, không phải trạng thái kết thúc. Mỗi bug bị reject phải có l | IDTS-Business-Rule.md
BR-13 | Tester có thể chỉnh sửa bug report sau khi submit | D. Business Rules về chỉnh sửa bug report | Tester có thể edit hoặc bổ sung thông tin sau khi bug đã được submit nếu bug chưa đóng. Tester có thể chỉnh: Description Steps to reproduce Expected result Actual result Module/category Priority/severity Evidence/screenshot Comment/feedback | IDTS-Business-Rule.md
BR-14 | Nếu bug đã assign, chỉnh sửa bug phải notify Developer | D. Business Rules về chỉnh sửa bug report | Nếu bug đã được assign cho Developer, sau khi Tester chỉnh sửa hoặc bổ sung thông tin, hệ thống cần thông báo cho Developer. Ví dụ notification: Bug report has been updated with additional information. Điều này giúp Developer không xử lý dựa trên thông tin cũ. | IDTS-Business-Rule.md
BR-15 | Phải assign Developer trước khi gửi Bug | D. Business Rules về chỉnh sửa bug report | Bug report không được gửi nếu chưa chọn Developer phụ trách. Tester phải chọn module/category trước. Sau đó, hệ thống sẽ hiển thị danh sách Developer phù hợp với module/category đó. Tester bắt buộc phải chọn một Developer trước khi nhấn nút Submit Bug. Nếu không có Developer phù hợp, hoặc tất cả Developer phù hợp đang có workload quá cao, hệ thống cho phép Tester chọn tùy chọn “Chưa có Developer phù hợp” ở cuối danh sách Developer. Khi Tester chọn “Chưa có Developer phù hợp” và submit bug, bug sẽ được ghi nhận với trạng thái Pending Assignment. Bug ở trạng thái này chưa được chuyển sang Developer review và cần được PM hoặc Tester theo dõi để assign Developer phù hợp sau đó. | IDTS-Business-Rule.md
BR-16 | Developer phải review thông tin bug sau khi nhận bug | E. Business Rules về Developer review bug | Sau khi nhận bug, Developer cần xem: Title Description Steps to reproduce Expected result Actual result Module/category Priority/severity Evidence Comments/history | IDTS-Business-Rule.md
BR-17 | Developer có thể yêu cầu thêm thông tin nếu bug chưa rõ | E. Business Rules về Developer review bug | Nếu thông tin bug chưa đủ rõ, Developer có thể chuyển bug sang trạng thái cần bổ sung thông tin. Các trường hợp phổ biến: Thiếu steps to reproduce Không có actual result Expected result không rõ Screenshot không đủ thông tin Module/category có thể sai Không mô tả được điều kiện xảy ra lỗi Luồng: Developer requests more information → Tester adds more information → Developer reviews bug again | IDTS-Business-Rule.md
BR-18 | Developer có thể thêm developer note | E. Business Rules về Developer review bug | Developer có thể thêm ghi chú kỹ thuật vào bug report. Ví dụ: Initial analysis Possible cause Related module Suggested next action Reason for status update Reason for rejection Developer note giúp tăng tính traceability của bug. | IDTS-Business-Rule.md
BR-19 | Developer có thể cập nhật trạng thái bug | E. Business Rules về Developer review bug | Developer được phép cập nhật trạng thái bug theo phạm vi xử lý. Ví dụ: Assigned In Review Need More Information In Progress Resolved Rejected Developer không nên tự ý đóng bug nếu nhóm muốn Tester hoặc PM xác nhận cuối cùng. | IDTS-Business-Rule.md
BR-20 | PM có quyền xem toàn bộ bug report | F. Business Rules về PM | PM có thể xem tất cả bug trong hệ thống để theo dõi tổng quan tiến độ. PM có thể filter theo: Status Priority/severity Module/category Developer Created date Updated date Overdue status | IDTS-Business-Rule.md
BR-21 | PM theo dõi workload của Developer | F. Business Rules về PM | PM có thể xem số lượng bug đang được assign cho từng Developer. Ví dụ: PM dùng thông tin này để đánh giá việc phân công có hợp lý không. | IDTS-Business-Rule.md
BR-22 | PM có thể yêu cầu reassign bug | F. Business Rules về PM | PM không nhất thiết trực tiếp reassign, nhưng có thể yêu cầu Tester reassign trong các trường hợp: Developer quá tải Bug overdue Bug lâu không cập nhật Bug bị assign sai module Bug có priority cao cần người khác xử lý nhanh hơn Nếu nhóm muốn PM có quyền mạnh hơn, PM có thể được phép trực tiếp reassign bug, nhưng cần ghi rõ trong authorization rule. | IDTS-Business-Rule.md
BR-23 | PM nhận escalation notification | F. Business Rules về PM | PM nên nhận thông báo khi có tình huống cần chú ý. Ví dụ: Bug priority high/critical chưa được assign Bug overdue Bug bị reassign nhiều lần Developer reject bug và hệ thống đã xác định follow-up owner Bug bị giữ ở Need More Information quá lâu Bug không được cập nhật trong thời gian quy định | IDTS-Business-Rule.md
BR-24 | Bug cần có trạng thái rõ ràng | G. Business Rules về status flow | Bộ status đề xuất: | IDTS-Business-Rule.md
BR-25 | Status transition phải có kiểm soát | G. Business Rules về status flow | Một số transition hợp lý: English clarification: Rejected must not be used as a silent terminal state. A transition to Rejected requires a rejection reason, history log, nextProcessor, and an allowed follow-up transition. Giải thích tiếng Việt: Rejected không được dùng như trạng thái kết thúc im lặng. Mọi transition sang Rejected phải có lý do reject, history log, nextProcessor và transition follow-up hợp lệ. | IDTS-Business-Rule.md
BR-26 | Closed bug không nên được chỉnh sửa tự do | G. Business Rules về status flow | Khi bug đã Closed: Không nên cho sửa trực tiếp nội dung chính Nếu phát hiện lỗi vẫn còn, nên tạo hành động Reopen Mọi thay đổi sau khi Closed phải được ghi lại trong history | IDTS-Business-Rule.md
BR-27 | Tester, Developer và PM có thể trao đổi qua comment | H. Business Rules về comment và feedback | Tester, Developer và PM có thể tham gia trao đổi trong phần comment của từng bug report. Comment dùng để hỗ trợ việc làm rõ thông tin, theo dõi tiến độ và ghi nhận trao đổi liên quan đến bug. Các quyền comment theo từng role: PM được phép comment vào bug nếu bug đó thuộc phạm vi dự án/team mà PM phụ trách. PM không thay thế Developer trong việc ghi developer note, và không thay thế Tester trong việc xác nhận thông tin bug. | IDTS-Business-Rule.md
BR-28 | Comment phải gắn với bug cụ thể | H. Business Rules về comment và feedback | Mỗi comment cần lưu: Comment content Người tạo comment Role của người tạo Thời gian tạo Bug liên quan Comment không được dùng để thay đổi trạng thái bug trực tiếp. Nếu nội dung comment dẫn đến thay đổi trạng thái, hệ thống cần ghi nhận thay đổi đó bằng status update và history log riêng. | IDTS-Business-Rule.md
BR-29 | Notification được gửi khi có sự kiện quan trọng | I. Business Rules về notification | Các trigger notification nên có: | IDTS-Business-Rule.md
BR-30 | Notification có thể dùng SAP BTP service hoặc bên thứ ba | I. Business Rules về notification | Notification module không nên khóa cứng vào một công nghệ duy nhất. Có thể dùng: SAP Build Process Automation Notification SAP Alert Notification Service Email Microsoft Teams Slack Telegram Third-party webhook | IDTS-Business-Rule.md
BR-31 | Hệ thống phải lưu lịch sử thay đổi của bug | J. Business Rules về audit/history | Mỗi thay đổi quan trọng nên được ghi vào history. Ví dụ: Create bug Edit bug information Assign bug Reassign bug Change status Add comment Upload evidence Request more information Reject bug Close bug Reopen bug | IDTS-Business-Rule.md
BR-32 | Bug history phải thể hiện ai làm gì và khi nào | J. Business Rules về audit/history | Mỗi history log nên có: Bug ID Action type Old value New value Người thực hiện Role Timestamp Note/reason nếu có Ví dụ: Bug \#102 changed status from Assigned to Need More Information by Developer A at 10:30 AM Reason: Missing steps to reproduce | IDTS-Business-Rule.md
BR-33 | Bug ID phải là duy nhất | K. Business Rules về dữ liệu | Mỗi bug report cần có một mã định danh duy nhất. Ví dụ: BUG-0001 BUG-0002 BUG-0003 Bug ID được dùng để search, track history, comment và assignment. | IDTS-Business-Rule.md
BR-34 | Một bug chỉ nên có một Developer chính tại một thời điểm | K. Business Rules về dữ liệu | Tại một thời điểm, bug nên có một assignee chính để tránh mơ hồ trách nhiệm. Nếu cần nhiều người xem hoặc hỗ trợ, có thể thêm watchers/collaborators sau. | IDTS-Business-Rule.md
BR-35 | Một Developer có thể được assign nhiều bug | K. Business Rules về dữ liệu | Developer có thể có nhiều bug cùng lúc, nhưng hệ thống hoặc PM cần theo dõi workload để tránh quá tải. | IDTS-Business-Rule.md
BR-36 | Bug có thể có nhiều comment, attachment và history logs | K. Business Rules về dữ liệu | Quan hệ dữ liệu nên là: Bug 1 - N Comments Bug 1 - N Attachments Bug 1 - N History Logs Bug N - 1 Developer Bug N - 1 Module Bug N - 1 Status | IDTS-Business-Rule.md
BR-37 | Người dùng có thể search/filter bug theo thông tin chính | L. Business Rules về search/filter | Tester, Developer và PM có thể search/filter theo: Bug ID Title Status Priority/severity Module/category Assignee Created by / Tester Created date Updated date PM có thêm nhu cầu filter theo: Overdue bugs Developer workload Bugs by module Bugs by status | IDTS-Business-Rule.md
BR-38 | Bug có thể bị đánh dấu overdue | M. Business Rules về overdue/escalation | Một bug có thể được xem là overdue nếu: Quá thời gian xử lý dự kiến Không được cập nhật trong một khoảng thời gian nhất định Priority cao nhưng chưa được assign Developer chưa phản hồi sau khi được assign Thời gian overdue có thể tùy nhóm quy định. Ví dụ: | IDTS-Business-Rule.md
BR-39 | Overdue bug nên notify PM | M. Business Rules về overdue/escalation | Khi bug bị overdue, hệ thống gửi notification cho PM để PM theo dõi hoặc yêu cầu reassign. | IDTS-Business-Rule.md
BR-40 | Hệ thống không xử lý việc sửa code trực tiếp | N. Business Rules về scope giới hạn | Developer có thể update status và note trong hệ thống, nhưng việc sửa code xảy ra ngoài hệ thống. Do đó, use case Fix Bug không nên đặt là chức năng chính của hệ thống. Nên dùng: Review Bug Information Update Bug Status Add Developer Note Request More Information thay vì: Fix Bug Deploy Fix Code Review | IDTS-Business-Rule.md
BR-41 | Hệ thống không thay thế Jira hoặc SAP Solution Manager hoàn chỉnh | N. Business Rules về scope giới hạn | Hệ thống chỉ tập trung vào quy trình defect reporting/tracking trong phạm vi đồ án. Không bao gồm: Full project management Sprint planning CI/CD Source code integration Complex approval workflow Full enterprise incident management | IDTS-Business-Rule.md
BR-42 | Bug classification phải tách SAP Module, Application Component và Defect Category | O. Business Rules cập nhật theo BA baseline hiện hành | Khi tạo hoặc cập nhật bug, hệ thống không nên gộp mọi thứ vào một field module/category mơ hồ. Mô hình phân loại hiện hành: Luồng lọc trên Fiori: Tester chọn SAP Module nếu liên quan -> hệ thống lọc Application Component -> hệ thống lọc Defect Category hợp lệ -> hệ thống lọc Developer theo Developer Responsibility. Với bug thuần IDTS, SAP Module có thể để trống hoặc chọn Not Applicable. | IDTS-Business-Rule.md
BR-43 | Bộ status chính phải bao gồm Retest Required | O. Business Rules cập nhật theo BA baseline hiện hành | Bộ status chính của IDTS: Reassigned không phải status chính. Reassign là action và phải được ghi nhận trong history log. English clarification: Rejected remains in the main status list, but it must always lead to a follow-up step. It must not be used as a silent terminal state. Giải thích tiếng Việt: Rejected vẫn nằm trong bộ status chính, nhưng luôn phải dẫn tới một bước xử lý tiếp theo. Không được dùng Rejected như trạng thái kết thúc im lặng. | IDTS-Business-Rule.md
BR-44 | Resolve phải đi qua bước xác nhận hoặc retest trước khi Closed | O. Business Rules cập nhật theo BA baseline hiện hành | Developer có thể chuyển bug sang Resolved khi đã có kết quả xử lý hoặc phản hồi xử lý. Sau Resolved: Developer không nên tự đóng bug nếu quy trình yêu cầu Tester/PM xác nhận cuối cùng. | IDTS-Business-Rule.md
BR-45 | nextProcessor phải được hệ thống cập nhật theo hành động tiếp theo | O. Business Rules cập nhật theo BA baseline hiện hành | nextProcessor là người cần thực hiện bước tiếp theo trên bug. Đây không phải role mới và không thay thế assignee. Backend CAP handler nên tự động cập nhật nextProcessor khi status, assignee hoặc assignment decision thay đổi. Mọi thay đổi quan trọng phải ghi history log. | IDTS-Business-Rule.md
BR-46 | Bug nên có lightweight test context và planning fields | O. Business Rules cập nhật theo BA baseline hiện hành | Để tăng traceability nhưng không xây full test management module, bug nên có các field optional: Để hỗ trợ PM monitoring, bug nên có thêm: Các field này không được dùng để mở rộng IDTS thành Jira, SAP Cloud ALM, SAP Solution Manager hoặc hệ thống test management đầy đủ. | IDTS-Business-Rule.md

## Risk Decision Log
Type | ID | Date / Likelihood | Description / Risk | Reason / Impact | Impact / Mitigation | Source
Decision | DEC-001 | 2026-05-28 | Use a split classification model: optional SAP Module, required Application Component, required Defect Category, inferred Component Category. | Avoid mixing SAP business modules with IDTS application features. | Data model and Fiori value helps must support dependent selection. | docs/pm/risk-decision-log.md
Decision | DEC-002 | 2026-05-28 | Use Developer Responsibility as the assignment mapping. | Assignment should be based on capability, not only a free-text developer field. | Assignee value help must filter by Component Category and optional SAP Module. | docs/pm/risk-decision-log.md
Decision | DEC-003 | 2026-05-28 | Keep `nextProcessor` as an automatically maintained action owner or queue. | PM and users need to know who must act next without changing the assignee concept. | CAP handlers must update nextProcessor and history logs on key actions. | docs/pm/risk-decision-log.md
Decision | DEC-004 | 2026-05-28 | Include `Retest Required` in the core status lifecycle. | Resolved does not always mean verified and closed. | Fiori actions and backend transitions must support retest pass/fail. | docs/pm/risk-decision-log.md
Decision | DEC-005 | 2026-05-28 | Split PM status to avoid one shared status file. | Multiple people may work concurrently and should not overwrite one shared status file. | Superseded by DEC-016, which uses member-owned status files instead of workstream-owned files. | docs/pm/risk-decision-log.md
Decision | DEC-006 | 2026-05-28 | Do not expand MVP into Jira, SAP Cloud ALM, SAP Solution Manager, CI/CD, source code management, or code review. | Keep scope aligned with the educational IDTS project. | Advanced enterprise features stay out of scope unless explicitly approved later. | docs/pm/risk-decision-log.md
Decision | DEC-007 | 2026-05-28 | Use SAP490 school deliverable templates as the external reporting baseline, but adapt ABAP-centric sections to SAP CAP/Fiori with supervisor confirmation. | The official SAP490 guide expects SAP configuration and SAP coding, while IDTS is implemented with SAP CAP Node.js and Fiori. | Final report and test evidence must map IDTS CAP/Fiori artifacts back to the required SAP490 chapters and templates. | docs/pm/risk-decision-log.md
Decision | DEC-008 | 2026-06-01 | Keep `Rejected` as a valid bug status, but define it as a follow-up status rather than a final state. | Mentor confirmed rejection is acceptable only when the following steps and responsible owner are explicit. | CAP handlers, Fiori actions, status matrix, and PM monitoring must require rejection reason, nextProcessor, and follow-up transition. | docs/pm/risk-decision-log.md
Decision | DEC-009 | 2026-06-01 | Use Product Discovery as the intake workflow for unclear IDTS requirements before BRD/SRS/FRS, diagrams, or implementation. | The team needs a repeatable BA method to avoid solution bias and scope creep. | New or unclear requirements should create discovery findings under `docs/ba/discovery/` before being promoted into specs or implementation tasks. | docs/pm/risk-decision-log.md
Decision | DEC-010 | 2026-06-01 | Store formal BRD/SRS/FRS deliverables in separate folders with separate English and Vietnamese markdown and DOCX files. | The team wants formal documents to be easier to review, submit, and maintain by language. | BRD uses `docs/ba/brd/`; SRS and FRS should follow the same folder and file pattern later. | docs/pm/risk-decision-log.md
Decision | DEC-011 | 2026-06-01 | Use SAP490 hybrid style for BRD/SRS/FRS: BRD stays business-first with light SAP implementation context, while SRS/FRS carry detailed technical and functional behavior. | The mentor needs SAP relevance, but BRD should not become a technical design document. | BRD v1.1 reduces technical depth and adds stakeholder needs, KPI, RACI, NFR, glossary, approval, and traceability. | docs/pm/risk-decision-log.md
Decision | DEC-012 | 2026-06-02 | Use `idts-ba-docx-deliverables` as the primary routing skill for IDTS BRD/SRS/FRS Markdown and DOCX work; use external document skills only as secondary references. | The team installed multiple external document skills, but IDTS needs SAP490 hybrid, language-split, and project-specific scope control. | Future BRD/SRS/FRS work should start with the IDTS skill, then selectively use `brd-creation`, `srs-documentation`, `frs-creation`, `docx`, and `docx-manipulation`. | docs/pm/risk-decision-log.md
Decision | DEC-013 | 2026-06-02 | Use a traditional SRS outline aligned with ISO/IEC/IEEE 29148-style requirement quality, and use FRS as the detailed functional workflow specification with diagrams and traceability. | The project needs mentor-readable documents while avoiding obsolete IEEE 830-only framing and keeping implementation details structured. | SRS v1.0 and FRS v1.0 become the requirement baseline for Sprint 1 planning, QA test design, and CAP/Fiori implementation traceability. | docs/pm/risk-decision-log.md
Decision | DEC-014 | 2026-06-03 | Use three active MVP roles: Tester, Developer, and PM. Reporter and Admin are not separate MVP roles. | The project is internal, Tester is the primary person who finds/reports bugs, and no dedicated Admin workflow is currently planned. | Canonical docs, BRD/SRS/FRS, BA support docs, diagrams, authorization rules, and PM handover must use Tester/Developer/PM as active roles. Reporter and Admin can be reconsidered after MVP if external reporting or formal admin flows are added. | docs/pm/risk-decision-log.md
Decision | DEC-015 | 2026-06-03 | Use `gws` as the preferred repeatable automation layer for SAP490 Google Drive/Docs/Sheets sync after installation and configuration; keep the Google Drive connector as the interactive automation environment fallback. | The team has multiple developers and needs repeatable commands that can run outside one chat thread. | Repository Markdown remains the source of truth; SAP490 DOCX/XLSX/PPTX artifacts are copied from templates and filled from approved sources; Google Docs/Sheets are review copies. Sync rules are documented in `docs/sap490/sync-workflow.en.md` and `docs/sap490/sync-workflow.vi.md`. | docs/pm/risk-decision-log.md
Decision | DEC-016 | 2026-06-03 | Use member-owned PM status files: DonHV, SangVN, DatDT, and NhanT. | The team wants each member to update their own work log to reduce merge conflicts and make weekly consolidation easier. | New threads must ask the user identity first, then read/update the matching file under `docs/pm/status/`. DonHV owns BA/PM consolidation and may support other lanes. | docs/pm/risk-decision-log.md
Decision | DEC-017 | 2026-06-04 | Add optional Learning Recap / Mentor Mode for nontrivial tasks. | The team wants AI-assisted work to also improve member understanding, especially for SAP CAP/Fiori, BA/PM, SAP490, and tooling decisions. | AGENTS.md routes this workflow and `.agents/skills/learning-recap` defines the teach-back process. It is optional and should not be forced after small tasks. | docs/pm/risk-decision-log.md
Decision | DEC-018 | 2026-06-04 | Use CAP CDS as the source of truth for IDTS database implementation; use `idts-database-modeling` and `database-schema-design` only as review/design support. | Generic database tools are useful for brainstorming, but IDTS is a SAP CAP project and should not drift into Prisma, Supabase, raw SQL, or vendor-specific modeling. | WP1 should start from `docs/ba/09-database-model-review.md`, `docs/ba/05-data-dictionary.md`, CAP MCP, and `sap-cap`; external schema artifacts remain optional documentation, not implementation source. | docs/pm/risk-decision-log.md
Decision | DEC-019 | 2026-06-04 | Adopt the DB-Q01 to DB-Q08 database modeling baseline for WP1. | The team needs concrete decisions before expanding `db/schema.cds`, especially for nextProcessor, Component Category derivation, rejection reason storage, attachments, bugNumber, optional SAP Module, and duplicate links. | `docs/ba/09-database-model-review.md`, `docs/project-context.md`, and the three IDTS canonical docs now define the WP1 database baseline. SangVN/Backend should use it before coding CDS. | docs/pm/risk-decision-log.md
Decision | DEC-020 | 2026-06-05 | Adopt the Sprint 02 mentor feedback baseline: developers may view/discuss team-visible bugs, lifecycle-changing actions remain controlled, developer notes are optional by default, selected transitions require note/reason, and Bug Detail UI must prioritize assignee/status and key input fields. DonHV leads Backend CAP/backend bug fixing; NhanT supports backend verification/QA; DatDT leads Fiori/UI5; SangVN supports Fiori/UI5. | Mentor confirmed rules/diagrams are settled enough and the team should focus on implementation/demo rather than redrawing analysis artifacts. | Canonical docs, Sprint 02 plan, Jira backlog, backend handlers, Fiori Bug Detail layout, and QA checks must follow this baseline. | docs/pm/risk-decision-log.md
Decision | DEC-021 | 2026-06-18 | Use the Object Page `Assignee` field and filtered value help as the single Fiori UI path for assignment/reassignment; remove the duplicate `Assign Developer` buttons from the UI while retaining backend action compatibility. | The field value help already has the correct classification context and avoids the competing action-parameter dialog. A single UI path reduces bugs and keeps assignment side effects centralized in draft save/update handling. | Fiori Object Page no longer exposes `Assign Developer` buttons. CAP handlers must treat `assignee_ID` changes as assignment/reassignment, derive status, update `nextProcessor`, write history, and create notification records. The backend action remains available for existing tests/API callers. | docs/pm/risk-decision-log.md
Decision | DEC-022 | 2026-06-20 | Use `Assignee (Technical Owner)` and `Current Action Owner` as the Sprint 3 ownership wording baseline, while keeping `assignee` and `nextProcessor` semantics unchanged and deferring any new `Cancel` status. | Mentor review showed the main gap is ownership clarity in the UI and monitoring views, not a need to rename persistence fields or expand the status catalog immediately. | Backend may add read-only display fields such as `currentActionOwnerDisplayName`, but Sprint 3 must not change the meaning of `assignee`, must keep `nextProcessor` as the current action owner or queue concept, and must not add `Cancel` unless a later explicit decision is approved. | docs/pm/risk-decision-log.md
Decision | DEC-023 | 2026-06-20 | Expose PM monitoring states as derived read-only service fields on `BugService.Bugs`, and keep current-action-owner filtering anchored on `nextProcessorUser` / `nextProcessorRole` instead of the display summary. | PM monitoring needs filterable OData fields for overdue and follow-up states, while `currentActionOwnerDisplayName` is readable text derived at read time and should not become the filtering key. | Backend/OData now exposes `isOverdue`, `isPendingAssignment`, `isRejectedFollowUp`, and `isRetestRequired` as filterable service fields. FE monitoring should filter user/queue ownership through `nextProcessorUser_ID` and `nextProcessorRole_code`, while using `currentActionOwnerDisplayName` only for display clarity. | docs/pm/risk-decision-log.md
Decision | DEC-024 | 2026-06-20 | Expose developer workload as a separate read-only aggregate entity `BugService.DeveloperWorkloads`, grouped by `assignee` as technical owner rather than by `nextProcessor`. | PM workload monitoring needs a stable OData contract for per-developer counts and overload detection, but reusing `Bugs` for grouped workload would blur ownership semantics and push aggregation complexity into FE. | Backend/OData now serves `DeveloperWorkloads` with open/overdue/current-action counts, per-status breakdown, effort total, workload limit, and `isOverloaded`. Active zero-load developers remain visible for capacity review, while inactive developers remain visible only if they still own open bugs that PM must resolve. | docs/pm/risk-decision-log.md
Decision | DEC-025 | 2026-06-21 | Keep `HistoryEvents` as the primary readable history contract and expose grouped change context through read-only service fields instead of changing persistence tables. | Sprint 3 needs an event-first UI5 timeline, but the raw audit source `HistoryLogs` should remain append-only detail instead of becoming the main UX payload. | Backend/OData now exposes `HistoryEvents.groupedChangeContext` and `HistoryEvents.changeCount` as read-only virtual fields derived at read time from `HistoryLogs`. FE should use `HistoryEvents` as the main timeline source and keep `HistoryLogs` as secondary expandable detail. | docs/pm/risk-decision-log.md
Decision | DEC-026 | 2026-06-21 | Keep SQLite as the default local runtime and treat PostgreSQL as a spike/profile until draft-media attachment flows are fixed or redesigned. | PostgreSQL deploy/read works, but HTTP draft activation fails with `function decode(bytea, unknown) does not exist` when `Attachments.content : LargeBinary` participates in draft activation. | Do not promote PostgreSQL as a supported profile yet. Phase 3 must decide between binary-in-DB with limits, CAP media/draft fix/upgrade, or metadata-in-DB plus external object/file storage. | docs/pm/risk-decision-log.md
Decision | DEC-027 | 2026-06-21 | Adopt external object storage as the long-term attachment architecture and use the SAP-supported `@cap-js/attachments` plugin as the preferred implementation path. | Current CAP/PostgreSQL package versions are already current, the custom `LargeBinary` draft path fails on PostgreSQL, and the official plugin provides draft-aware streaming, validation, and object-store providers without requiring a custom storage framework. | Jira `IDTS-31` implements the migration. Attachment metadata/reference remains in CAP persistence; file bytes move to bound object storage. SQLite remains the local default, and PostgreSQL support remains blocked until non-DB storage regression passes. | docs/pm/risk-decision-log.md
Decision | DEC-028 | 2026-06-21 | Use one shared PostgreSQL environment as the team integration database while keeping SQLite as each developer's default local database. | The team wants one consistent integration state without requiring every developer to run PostgreSQL locally. | Profile `integration` targets PostgreSQL and standard object storage. Credentials stay in ignored private configuration. Schema deployment is coordinated by an environment owner; other developers normally connect without redeploying. | docs/pm/risk-decision-log.md
Decision | DEC-029 | 2026-06-21 | Do not add a custom MinIO adapter to IDTS after the stock attachment-plugin spike failed on virtual-hosted bucket addressing. | The short spike proved CAP/PostgreSQL and attachment metadata work, but binary upload resolved `idts-attachments.localhost`; supporting local MinIO would require path-style/DNS work or plugin customization outside the approved SAP-supported scope. | Final IDTS-31 acceptance must use a supported SAP Object Store, native AWS S3, Azure Blob Storage, or GCP Cloud Storage binding. S3-compatible providers that require custom endpoints, including Cloudflare R2, need explicit stock-plugin compatibility proof first. | docs/pm/risk-decision-log.md
Decision | DEC-030 | 2026-06-21 | Use a private native AWS S3 bucket as the accepted external object store for the current IDTS integration environment. | The stock `@cap-js/attachments` S3 adapter passed upload, activation, download, history, PostgreSQL binary-absence, and delete cleanup without custom code. | IDTS-31 is Done. PostgreSQL stores attachment metadata/reference while AWS S3 stores file bytes. Credentials remain private and the bucket remains non-public. | docs/pm/risk-decision-log.md
Decision | DEC-031 | 2026-06-22 | Maintain source-code knowledge mirrors for every tracked file under `app/`, `srv/`, and `db`. | The team needs beginner-friendly explanations that show how Fiori, CAP services, and CDS/data files connect, especially for members learning CAP/Fiori. | Any future task that creates or changes a tracked source file in those folders must create or update the matching mirror note under `docs/knowledge/app/`, `docs/knowledge/srv/`, or `docs/knowledge/db/`, including explicit cross-folder links and safe-edit notes. | docs/pm/risk-decision-log.md
Decision | DEC-032 | 2026-06-27 | Implement IDTS login as custom email/password authentication in CAP Node.js, and implement email notification through real SMTP with delivery/outbox tracking. | The team does not expect to have SAP BTP/XSUAA access, but still needs real login and real email behavior. SMTP must be real, but email failure must not break bug workflow actions. | Jira IDTS-34 to IDTS-38 split the work across backend auth, FE login, SMTP delivery, notification UI/readability, and QA regression. Secrets stay in private config; `Users` remains the internal profile/role source. | docs/pm/risk-decision-log.md
Decision | DEC-033 | 2026-06-29 | Use `AuthService`, `Users.passwordHash`, server-side `AuthSessions`, and Bearer-token request mapping as the IDTS-34 backend auth foundation. | Frontend login work needs a concrete OData contract, but the project still has no near-term SAP BTP/XSUAA account path. Keeping the session record server-side lets IDTS revoke sessions and avoids storing raw tokens in the database. | FE login should call `AuthService.login`, store the returned bearer token on the client side, send it as `Authorization: Bearer <token>` for protected OData calls, call `logout` to revoke the session, and use `me()` to restore the current user. Plaintext passwords, raw tokens, auth secrets, and private endpoints must stay out of source, docs, Jira, and logs. | docs/pm/risk-decision-log.md
Decision | DEC-034 | 2026-07-01 | Adopt QA Depth Gate as the mandatory evidence and review baseline for PRs that change `app/`, `srv/`, `db`, `scripts/qa`, workflow, or package files. | IDTS-32 showed that happy-path-only QA missed invalid input, role, persistence, and UI/UX defects. The team needs a repeatable gate that forces falsification-first evidence, not just clean demo output. | PRs into `dev` must include positive, negative, edge/boundary, role/authorization, persistence/reload, UI/UX, known-gaps, and Jira/evidence sections. The `qa-depth-gate` workflow validates PR body structure, runs fast regression lanes, runs secret scan, and should become required branch protection after landing. | docs/pm/risk-decision-log.md
Decision | DEC-035 | 2026-07-01 | Use Render as the near-term shared QA deployment platform for IDTS. | The team needs a shared URL for login, OData, SMTP/outbox, and attachment testing without requiring every member to run PostgreSQL, Brevo SMTP credentials, and AWS S3 credentials locally. Render Blueprint deployment is simpler than ECS for this QA/demo phase. | Add `render.yaml`, use the CAP `integration` profile with PostgreSQL, keep AWS S3 and Brevo SMTP credentials in Render private env vars, and document first-time schema/password setup. ECS/App Runner can remain a later AWS-native path after shared QA stabilizes. | docs/pm/risk-decision-log.md
Decision | DEC-036 | 2026-07-02 | Use each member's real FPT email as both the shared-QA login identity and notification recipient, while keeping real addresses out of Git/Jira evidence. | DonHV selected recipient-realism over single-recipient test mode. The current `Users.email` field is already the login identifier and SMTP recipient source. | Update cloud users by stable UUID through private environment variables, normalize addresses to lowercase, revoke old sessions, keep local seed aliases unchanged, and rerun the cloud identity helper after any seed-reloading DB deploy. | docs/pm/risk-decision-log.md
Decision | DEC-037 | 2026-07-02 | Use Brevo Transactional Email HTTP API as the shared-QA mitigation for Render SMTP timeout, while keeping SMTP as the local/fallback transport. | Render can create email outbox rows but SMTP to Brevo timed out on ports 587 and 2525; local SMTP verification passed, pointing to deployment/network reachability rather than a broken outbox model. HTTPS API calls are easier to run from Render and easier to test with a fake HTTP server. | Add provider-neutral email config, implement `brevo-api` sender, keep `NotificationDeliveries` unchanged, store API key only in private Render env, and verify provider success/failure through fake HTTP integration plus one real Render smoke. | docs/pm/risk-decision-log.md
Decision | DEC-038 | 2026-07-07 | Add AI only as an optional, human-reviewed suggestion layer for duplicate detection, classification, summaries, and Smart Assign explanation. | The team wants useful AI assistance without allowing probabilistic output to own assignments, classification persistence, duplicate confirmation, or lifecycle transitions. | IDTS-63 defines the data boundary, failure fallback, human-review rules, and audit baseline. Only IDTS-63 enters Sprint 4; provider, audit model, feature, security, and QA implementation move to Sprint 5. CAP validation and authorization remain final. | docs/pm/risk-decision-log.md
Decision | DEC-039 | 2026-07-07 | Protect Render shared-QA continuity by taking a private logical PostgreSQL backup first, then prefer upgrading the existing Render PostgreSQL database if shared QA remains needed after expiry. | Render QA is already accepted for login, OData, Brevo API, and AWS S3 attachments; changing providers now adds cutover, credential, SSL/network, and retest risk. Render's current Free PostgreSQL policy has no managed backup support and a fixed expiry window, so a manual backup is required before any upgrade or migration. | `IDTS-45` adds a secret-safe backup helper and evidence instructions. Actual dumps stay outside Git/Jira. Migration to another PostgreSQL provider remains a fallback if Render upgrade is not approved before 2026-07-24. | docs/pm/risk-decision-log.md
Decision | DEC-040 | 2026-07-08 | Implement IDTS-66 with a database-portable, bounded on-demand embedding scan plus deterministic text/classification fallback; do not introduce pgvector in this feature task. | IDTS must keep SQLite local development and PostgreSQL QA portability, the current provider seam supports one embedding request at a time, and the QA dataset is small. Adding a provider-specific vector extension now would expand deployment and migration scope before a real provider is selected. | `suggestSimilarBugs` scans at most 50 recently modified bugs with four embedding calls in parallel, never writes `DuplicateLinks`, and remains useful when AI is unavailable. A production-scale vector index or pgvector design requires a separate reviewed infrastructure task and migration/performance evidence. | docs/pm/risk-decision-log.md
Decision | DEC-041 | 2026-07-12 | Enforce file-plus-flow ownership and an Ownership Knowledge Gate for all four members from 2026-07-13. | Mentor review showed that a working feature is not sufficient when the team cannot trace, debug, or explain the code and its dependencies. | A first daily gate starts with three questions and adds one per inactive ownership-code day, capped at seven; a new flow later that day adds two questions. PASS requires 80%, all critical answers, a real debug exercise, and teach-back. FAIL permits supervised learning but blocks PR merge and Jira Done until retest PASS. | docs/pm/risk-decision-log.md
Decision | DEC-042 | 2026-07-22 | Organize the SAP490 mentor-review Drive into current/templates/archive and prefix every descendant folder and file with `SU26SAP01_GSU26SAP01_`; keep the root as `SU26SAP01_GSU26SAP01`. | The prior root mixed current, previous, POC/demo, Workshop, and template files, and unprefixed folder names did not follow the project/group naming convention. | Move/rename rather than copy, preserve all existing IDs/links, never delete, place uncertain duplicates in the prefixed `Duplicates_To_Review` folder, and treat repository artifacts as source of truth. UAT Prepared and the Final Project Report template remain disclosed limitations, not completed evidence or P1 document defects. | docs/pm/risk-decision-log.md
Decision | DEC-043 | 2026-07-22 | Withdraw the SAP490 `CONDITIONALLY READY` verdict and reopen `DOC-20260725` as `NOT READY`. | A complete exact-current OfficeCLI and diagram audit found 10/31 schema failures, non-IDTS Blueprint content, severe spreadsheet readability defects, stale images in the Diagram Pack, and lifecycle inaccuracies in several diagram sources. | Complete the P1 list in `docs/pm/evidence/mentor-readiness-20260725-full-office-diagram-audit.md`, then rerun the full 31-artifact OfficeCLI/visual gate and 21-diagram semantic/render gate before restoring any readiness claim. | docs/pm/risk-decision-log.md
Decision | DEC-044 | 2026-07-22 | Use Jira Epic `IDTS-88` as the Sprint 5 delivery boundary and reparent all 11 current Sprint 5 issues from the Sprint 4 epic or no parent. | Sprint 5 existed on the board without an Epic, leaving its work structurally split and weakening status reporting. | Keep mentor readiness, Shared QA/infrastructure, security follow-up, UX carry-over, and ownership governance visible under one Epic; retain existing issue links and reconcile each child truthfully before Sprint 5 closure. | docs/pm/risk-decision-log.md
Decision | DEC-045 | 2026-07-22 | Restore the SAP490 mentor-pack verdict to `CONDITIONALLY READY` after closing the reopened Office/diagram P1 findings. | Fresh final evidence reports 31/31 Office artifacts schema-valid with zero issues, 21/21 diagram manifest verification, a current 46-slide Diagram Pack, preserved Drive IDs, and zero root loose files. | Mentor review may use the current pack, but three Pending suites, UAT execution/sign-off, Final Project Report, approvals, and Knowledge Gate remain separate open limitations and must not be represented as complete. | docs/pm/risk-decision-log.md
Decision | DEC-046 | 2026-07-23 | Withdraw the restored SAP490 `CONDITIONALLY READY` verdict and reopen `DOC-20260725` as `NOT READY` after independent content and semantic verification. | The automated 31/31 OfficeCLI gate is reproducibly clean, but it does not detect the `vx.x` placeholder remaining in both Test Report workbooks; Diagram 07 also shows a post-retest Request More Information path that the runtime state machine does not support. | Correct the two P1 findings at the existing Drive IDs, rerun token/OfficeCLI/visual/diagram-semantic gates, read back Drive, and update Mentor Index last. Keep Blueprint depth as a P2 follow-up and do not alter Knowledge Gate or claim UAT/sign-off. | docs/pm/risk-decision-log.md
Decision | DEC-047 | 2026-07-23 | Restore SAP490 mentor-pack status to CONDITIONALLY READY after closing the independent recheck findings at the same Drive IDs. | Test Report EN/VI now use the exact v0.3 identifier with no broken names; Diagram 07 is aligned with the runtime transition allow-list; Blueprint EN/VI are expanded to 20 pages; fresh gates report 31/31 Office PASS/zero issues, 21/21 diagrams, and native Slides 46/46/46/0 legacy. | Documentation remediation may close, but three Pending suites, UAT execution/sign-off, Final Project Report, approvals, and Knowledge Gate stay explicitly open. No runtime merge or project-completion claim follows from this decision. | docs/pm/risk-decision-log.md
Decision | DEC-048 | 2026-07-23 | Keep the SAP490 artifact verdict at CONDITIONALLY READY but reopen DOC-20260725 governance closeout. | A second active verification reproduced the 31/31 Office and 21/21 diagram gates, but Jira IDTS-78 is Done without the mandatory `Ownership Knowledge Gate: PASS`; the latest Jira evidence explicitly leaves the gate In Progress. | Reopen IDTS-78 until genuine dedicated-learning-thread PASS evidence exists. Do not infer or backfill PASS from document quality. Clean the repackaged local Blueprint template and temporary rebuilt copies before repository commit. | docs/pm/risk-decision-log.md
Decision | DEC-049 | 2026-07-23 | Use `docs/qa/test-catalog.json` as the single source for the 12 current SAP490 test workbooks and define test metrics by explicit denominator. | Separate template filling caused EN/VI drift, wrong test-type classification, empty predicted results, stale suite totals, and ambiguous “coverage” labels. | Generate EN/VI Scenario, Unit, Functional, Report, UAT Prepared, and Defect workbooks from the canonical catalog; validate case/evidence/status parity; report case execution rate, pass rate over executed cases, planned requirement traceability, executed requirement coverage, and suite execution rate separately. UAT Prepared and Not Run never count as Pass. | docs/pm/risk-decision-log.md
Decision | DEC-050 | 2026-07-23 | Treat the official SAP490 workbook structure as a mandatory output contract while keeping the canonical test catalog as the content source. | A normalized-table rewrite passed content checks but removed official sheets, merges, images, and template layout; Google Sheets also exposed a duplicated percent symbol that schema checks did not detect. | Fill official templates in place, protect sheet/merge/image/print contracts with an automated fidelity test, require cross-renderer visual review, and fix renderer-specific findings in source before same-ID Drive update. | docs/pm/risk-decision-log.md
Decision | DEC-051 | 2026-07-23 | Require a minimum 12pt font for every populated mentor-facing cell in the current SAP490 test workbooks. | Google Sheets exposed unreadably small body text and narrow result fields that split `Passed` across lines even though earlier structural gates passed. | Enforce the rule at generator and validator source, retain official template structure, and require OfficeCLI plus LibreOffice and Google Sheets visual review before same-ID Drive synchronization. | docs/pm/risk-decision-log.md
Decision | DEC-042 | 2026-07-23 | Give every named public Bug workflow OData action that writes History one dedicated ActionType, while retaining all legacy categories and historical rows. | Mentor review requires `HistoryEvents.actionType_code` to identify the initiating command without inferring it from status or child logs. | IDTS-89 maps 11 workflow commands one-to-one, copies the exact code to HistoryLogs, preserves legacy reads and generic-edit categories, and rolls out PostgreSQL code-list rows by dry-run-first idempotent UPSERT without `cds deploy` or data reset. | docs/pm/risk-decision-log.md
Risk | RISK-001 | Current CAP model is too small for MVP. | High | High | Start Sprint 1 with CDS model foundation before Fiori work. | docs/pm/risk-decision-log.md
Risk | RISK-002 | Team may confuse SAP Module with IDTS feature/module. | Medium | High | Use glossary, data dictionary, and UI labels consistently. | docs/pm/risk-decision-log.md
Risk | RISK-003 | nextProcessor may be misunderstood as a second assignee. | Medium | Medium | Keep UI and docs clear: assignee owns technical work, nextProcessor shows the next action owner. | docs/pm/risk-decision-log.md
Risk | RISK-004 | Parallel edits may create merge conflicts in status docs. | Medium | Medium | Use one status file per member, one task file per work package, and DonHV-only consolidation for shared docs/Sheets/Excel. | docs/pm/risk-decision-log.md
Risk | RISK-005 | Fiori work may start before model/service value helps are stable. | Medium | High | Gate Fiori implementation behind WP1 and WP2. | docs/pm/risk-decision-log.md
Risk | RISK-006 | Overengineering could turn IDTS into a full ITSM or Jira clone. | Medium | High | Check changes against BA scope and out-of-scope list before implementation. | docs/pm/risk-decision-log.md
Risk | RISK-007 | SAP490 guide may be interpreted as requiring classic SAP configuration and ABAP deliverables, while IDTS is a SAP CAP/Fiori project. | Medium | High | Confirm with supervisor that SAP BTP/CAP/Fiori artifacts satisfy SAP Coding, and add a mapping table from SAP490 sections to IDTS deliverables. | docs/pm/risk-decision-log.md
Risk | RISK-008 | Rejected bugs may be left without a clear owner or next action. | Medium | High | Enforce rejection reason, nextProcessor, notification, history log, and allowed follow-up transitions in backend and UI. | docs/pm/risk-decision-log.md
Risk | RISK-009 | Product Discovery may slow down simple confirmed work if applied too heavily. | Low | Medium | Use it for new, unclear, or business-impacting requests; skip it for trivial factual answers and already-confirmed implementation tasks. | docs/pm/risk-decision-log.md
Risk | RISK-010 | Google Docs/Sheets review copies may drift from repository source if feedback is edited directly in Google Workspace and not synced back. | Medium | High | Update repository source first, recreate template-filled local DOCX/XLSX/PPTX files, then sync Google copies. Use `docs/sap490/sync-workflow.en.md` and `docs/sap490/sync-workflow.vi.md`; avoid committing local Google credentials or Drive IDs. | docs/pm/risk-decision-log.md
Risk | RISK-011 | Learning Recap may slow down delivery if applied after every small task. | Medium | Low | Keep it optional. Offer it after nontrivial tasks and activate it when the user asks or agrees. | docs/pm/risk-decision-log.md
Risk | RISK-012 | Generic database tools may push the project away from CAP/CDS patterns or hide business meaning behind generic SQL tables. | Medium | High | Treat CAP CDS and IDTS BA documents as authoritative. Use database skills and external schema artifacts only as secondary review aids, then verify CAP syntax with CAP MCP and `cds compile srv --to edmx`. | docs/pm/risk-decision-log.md
Risk | RISK-013 | Developers may misunderstand wider visibility as permission to process any bug. | Medium | High | Separate view/comment permission from lifecycle-changing actions in backend handlers, Fiori UI actions, QA tests, and documentation. | docs/pm/risk-decision-log.md
Risk | RISK-014 | Shared PostgreSQL migration may fail or lose legacy attachment evidence if old custom attachment tables are dropped without coordination. | Medium | High | Use a new integration database/schema or take an approved backup/export before legacy table removal. CAP's drop-table guard must not be bypassed casually. | docs/pm/risk-decision-log.md
Risk | RISK-015 | External object-storage behavior may differ from the verified DB fallback. | Medium | High | Bind one shared object store to profile `integration` and rerun draft upload/activate/download/history acceptance before moving `IDTS-31` to Done. | docs/pm/risk-decision-log.md
Risk | RISK-016 | An S3-compatible provider may still be incompatible with the stock plugin because it requires a custom endpoint, path-style addressing, or provider-specific behavior. | Medium | High | Run a short provider compatibility gate before adoption. Do not customize the attachment plugin unless a separate architecture decision explicitly accepts the maintenance cost. | docs/pm/risk-decision-log.md
Risk | RISK-017 | Long-lived AWS IAM access keys may be exposed, forgotten, or remain active beyond the project/free-credit period. | Medium | High | Keep keys only in ignored private configuration/password storage, use least-privilege bucket policy, rotate regularly, deactivate unused keys, and configure AWS budget alerts. | docs/pm/risk-decision-log.md
Risk | RISK-018 | Custom login and SMTP delivery may introduce security defects or secret leakage if implemented casually. | Medium | High | Store only password hashes, keep auth/SMTP secrets in ignored private config, scan docs/code before commit, use safe error messages, test wrong-password/inactive-user/invalid-token paths, and keep email sending out of the core workflow transaction. | docs/pm/risk-decision-log.md
Risk | RISK-019 | Custom Bearer-token auth may be wired incorrectly in the CAP HTTP runtime or FE may store/send the token unsafely. | Medium | High | Keep the auth middleware small, test login/wrong-password/inactive/revoked-session paths, verify CAP compile after adding `AuthService`, document the FE contract clearly, and require IDTS-35/IDTS-38 browser or HTTP evidence that protected OData calls use the token correctly. | docs/pm/risk-decision-log.md
Risk | RISK-020 | SMTP delivery is at-least-once, so an application crash after the provider accepts a message but before IDTS commits `SENT` can cause a retry and duplicate email. | Low | Medium | Use one delivery row per notification/channel, bounded worker locks, provider message IDs, retry limits and readable event IDs. Accept the residual risk for v1; do not claim exactly-once delivery unless a provider-supported idempotency design is added later. | docs/pm/risk-decision-log.md
Risk | RISK-021 | QA Depth Gate can become a checkbox exercise or slow urgent fixes if evidence quality is weak or too broad. | Medium | Medium | Keep PR evidence falsification-first, require concrete reasons for `N/A`, link actionable defects to Jira, and allow scoped DonHV-approved exceptions only when the status log records the reason and follow-up. | docs/pm/risk-decision-log.md
Risk | RISK-022 | Render shared QA can fail or leak sensitive operational data if secrets are entered into source/docs/Jira/logs or if first-time DB/password setup is run against the wrong environment. | Medium | High | Use `sync: false` env vars for AWS/Brevo secrets, keep email disabled by default, document Render Shell commands, run secret scan before merge, and verify logs do not print credentials, bearer tokens, private recipients, or provider message IDs. | docs/pm/risk-decision-log.md
Risk | RISK-023 | CAP startup on Render can expose database credentials when CAP logs connected service credentials at info level. | Medium | High | Configure CAP logger levels for both `cds` and `cds.serve` as `warn` in package config, set `CDS_LOG_LEVEL=warn` for Render QA, avoid `cds_log_levels` env because it can override the object config as a string, verify logs do not contain `postgresql://`, and rotate/delete any temporary database credential if it appears in logs. | docs/pm/risk-decision-log.md
Risk | RISK-024 | The free Render PostgreSQL instance expires on 2026-07-31 and may remove the shared QA data if no action is taken. | High | High | Track [IDTS-45](https://dutassociation.atlassian.net/browse/IDTS-45), due 2026-07-24; use `npm run render:db:backup` with a private `RENDER_QA_DATABASE_URL`, store the dump outside Git/Jira, restore to a temporary PostgreSQL target, and upgrade Render PostgreSQL unless migration is explicitly approved. | docs/pm/risk-decision-log.md
Risk | RISK-025 | Render shared QA may not be able to reach Brevo SMTP even when credentials verify locally. | Medium | Medium | Keep IDTS email outbox/retry behavior accepted separately from provider delivery. Current evidence: local Nodemailer verify to Brevo passes, Render delivery creates outbox rows but fails with sanitized `ETIMEDOUT` on ports 587 and 2525. Next mitigation is provider/network investigation or a different SMTP/API provider for shared QA. | docs/pm/risk-decision-log.md
Risk | RISK-026 | Brevo API migration can leak API keys or real recipient data if tests/logs/Jira evidence print request headers or payloads carelessly. | Medium | High | Keep API key only in private env, fake Brevo API tests must not print headers, logs must only show counts/status/provider, and secret scan must pass before PR. Real Render smoke evidence should record delivery status only, not full recipient/API key/provider message-id. | docs/pm/risk-decision-log.md
Risk | RISK-027 | AI provider payloads or generated output may leak sensitive data, follow prompt injection, hallucinate facts, or influence users as if suggestions were authoritative. | Medium | High | Enforce feature-specific field allowlists, redaction, length limits, safe text rendering, bounded timeout/retry, human review, backend-owned audit writes, and CAP validation/authorization. Keep AI disabled by default and preserve the non-AI workflow. | docs/pm/risk-decision-log.md
Risk | RISK-028 | On-demand duplicate embeddings may become slow or expensive when the bug dataset grows beyond the small QA baseline, and the 50-record recency cap may miss older semantic matches. | Medium | Medium | Keep IDTS-66 explicitly bounded and suggestion-only, monitor candidate quality/latency, and create a separate vector-index/pgvector task before production-scale adoption. Do not raise the cap casually without provider-cost and performance evidence. | docs/pm/risk-decision-log.md
Risk | RISK-029 | Knowledge Gate may become rote memorization, be bypassed manually in Jira, or become too burdensome for trivial work. | Medium | Medium | Ask flow/debug reasoning instead of line trivia; retain mentor hints and teach-back; start only from 2026-07-13 with zero historical debt; cap question count at seven; and require DonHV/agent operational review because Jira workflow cannot technically prevent an administrator bypass. | docs/pm/risk-decision-log.md
Risk | RISK-030 | A partial validation scope or standalone-asset update can leave the mentor navigation index and composite Diagram Pack claiming current/readable artifacts that are still stale or invalid. | High | High | Treat the current-review folder as one release unit: validate every Office artifact, compare embedded deck assets with final standalone diagrams, visually inspect normal review scale, and update Mentor Index/readiness only after the whole-pack gate passes. | docs/pm/risk-decision-log.md
Risk | RISK-031 | Sprint 5 may miss its closure target because 0/11 issues are Done, five are overdue, and DonHV owns 9/11 issues. | High | High | Reconcile actual evidence/status by 2026-07-24, set dates for IDTS-80/81, explicitly close or defer overdue work, and rebalance support/evidence tasks to NhanT and DatDT where appropriate without bypassing ownership or Knowledge Gate rules. | docs/pm/risk-decision-log.md
Risk | RISK-032 | Jira can show documentation work as Done even when the mandatory Ownership Knowledge Gate evidence is absent. | High | High | Treat Jira workflow state as insufficient by itself; require a comment containing `Ownership Knowledge Gate: PASS` plus matching evidence before Done, and reopen IDTS-78 until that condition is genuinely met. | docs/pm/risk-decision-log.md

## Open Questions
Source | Section | Column 1 | Column 2 | Column 3 | Column 4
docs/ba/brd/brd.en.md | 21. Open Questions | OQ-001 | Does the supervisor accept SAP CAP/Fiori artifacts as the SAP Coding deliverable in SAP490 templates? | Team / Mentor
docs/ba/brd/brd.en.md | 21. Open Questions | OQ-002 | Should PM have direct assignment/reassignment permission in MVP, or only request reassignment? | Team / Mentor
docs/ba/brd/brd.en.md | 21. Open Questions | OQ-003 | Which notification channels are required for MVP: in-app records only, email, SAP BTP service, or third-party channels? | Team / Mentor
docs/ba/brd/brd.en.md | 21. Open Questions | OQ-004 | Which attachment storage approach is acceptable for the project stage? | Team / Mentor
docs/ba/brd/brd.en.md | 21. Open Questions | OQ-005 | What exact SLA or overdue thresholds should be used for High, Medium, and Low priority bugs? | Team / PM
docs/ba/srs/srs.en.md | 13. Open Issues | OI-SRS-001 | Confirm whether PM can directly assign/reassign in MVP or only request reassignment. | Team / Mentor | Authorization and Fiori action visibility.
docs/ba/srs/srs.en.md | 13. Open Issues | OI-SRS-002 | Confirm notification delivery scope for MVP. | Team / Mentor | Whether notification records are enough.
docs/ba/srs/srs.en.md | 13. Open Issues | OI-SRS-003 | Confirm attachment storage approach. | Team / Mentor | File storage design and test evidence handling.
docs/ba/srs/srs.en.md | 13. Open Issues | OI-SRS-004 | Confirm overdue thresholds by priority/severity. | Team / PM | PM dashboard and escalation logic.
docs/ba/srs/srs.en.md | 13. Open Issues | OI-SRS-005 | Confirm SAP490 acceptance of CAP/Fiori artifacts as SAP Coding deliverables. | Team / Mentor | Final report structure and evidence mapping.
docs/ba/frs/frs.en.md | 9. Open Issues | OI-FRS-001 | Confirm PM direct reassignment permission. | Team / Mentor | Determines whether PM sees Assign/Reassign actions or only request/comment actions.
docs/ba/frs/frs.en.md | 9. Open Issues | OI-FRS-002 | Confirm notification channel for MVP. | Team / Mentor | Determines whether notification records alone satisfy MVP.
docs/ba/frs/frs.en.md | 9. Open Issues | OI-FRS-003 | Confirm attachment storage approach. | Team / Mentor | Determines whether Attachments are metadata-only or actual file handling.
docs/ba/frs/frs.en.md | 9. Open Issues | OI-FRS-004 | Confirm overdue thresholds and workload limits. | Team / PM | Determines PM dashboard calculations.
docs/ba/frs/frs.en.md | 9. Open Issues | OI-FRS-005 | Confirm whether Mermaid diagram source in Markdown should be rendered as images for DOCX submission. | Team / Mentor | Affects final DOCX visual format only, not functional scope.
docs/pm/tasks/ba3-srs-frs-deliverables.md | Remaining Open Issues | OI-001 | Confirm PM direct reassignment permission. | Team / Mentor
docs/pm/tasks/ba3-srs-frs-deliverables.md | Remaining Open Issues | OI-002 | Confirm notification delivery scope for MVP. | Team / Mentor
docs/pm/tasks/ba3-srs-frs-deliverables.md | Remaining Open Issues | OI-003 | Confirm attachment storage approach. | Team / Mentor
docs/pm/tasks/ba3-srs-frs-deliverables.md | Remaining Open Issues | OI-004 | Confirm overdue thresholds and workload limits. | Team / PM
docs/pm/tasks/ba3-srs-frs-deliverables.md | Remaining Open Issues | OI-005 | Confirm whether Mermaid diagrams must be rendered as images in DOCX for submission. | Team / Mentor
docs/pm/tasks/ba3-srs-frs-deliverables.md | Open issues còn lại | OI-001 | Xác nhận quyền PM direct reassignment. | Team / Mentor
docs/pm/tasks/ba3-srs-frs-deliverables.md | Open issues còn lại | OI-002 | Xác nhận notification delivery scope cho MVP. | Team / Mentor
docs/pm/tasks/ba3-srs-frs-deliverables.md | Open issues còn lại | OI-003 | Xác nhận attachment storage approach. | Team / Mentor
docs/pm/tasks/ba3-srs-frs-deliverables.md | Open issues còn lại | OI-004 | Xác nhận overdue thresholds và workload limits. | Team / PM
docs/pm/tasks/ba3-srs-frs-deliverables.md | Open issues còn lại | OI-005 | Xác nhận Mermaid diagrams có cần render thành hình trong DOCX khi nộp hay không. | Team / Mentor