## Cover
Functional Test
| Module | IDTS | Module Name | Issue and Defect Tracking System in SAP
| Function ID | IDTS-SAP490-FUNCTIONAL
| Function Name | Current CAP/Fiori functional verification
| Created Date | 2026-07-23 | Last Update Date | 2026-07-23
|  |  | Approver | Reviewer | Creator
DonHV

## Histories
No | Version | Description | Sheet | Modified date | Modified by
1 | 0.3 | Filled functional cases, exact programmatic runs and concrete test-data descriptions in the official template. | Test Cases, Test Result, Test Data Description | 2026-07-23 | DonHV

## Test Cases
Business Flow |  | Function Name |  | Created/Updated by | Created date |  | Reviewed by |  | Reviewed Date
IDTS SAP490 functional verification |  | CAP/Fiori current baseline |  | DonHV | 2026-07-23 |  | Mentor / Supervisor |  | Pending review
NO. | Test Contents |  |  |  | Test Results |  |  |  | Evidence / limitations
| Test Cases |  | Predicted Test Results |  | Tester | Test Date |  | Result
FT-CREATE-001 | Create a valid bug through the service — Tester Req: SRS-FR-BUG-001, SRS-FR-CLASS-003 Steps: 1) Submit a valid create request. ¦ 2) Read the created bug by ID. ¦ 3) Check required business values. |  | Preconditions: Tester is authenticated; active priority, severity and environment codes exist. Data: Complete sanitized bug payload with active codes. Expected: Create succeeds and the bug is persisted with valid values. Actual / postcondition: Passed: valid active catalog codes created a bug. ¦ Created test data remains only in the in-memory database. |  | DonHV | 2026-07-23T10:59:07+07:00 |  | Passed | Command: npm run qa:idts41:programmatic Evidence: scripts/qa/test-idts41-code-list-validation.js Defects / limit: IDTS-32 ¦ No fresh Fiori UI or reload evidence.
FT-VALID-001 | Reject invalid, blank and inactive catalog values — Tester Req: SRS-FR-BUG-002, SRS-FR-CLASS-003, SRS-FR-STATUS-008 Steps: 1) Submit each invalid create/update/draft variant. ¦ 2) Check 400 response and target field. ¦ 3) Reload persisted row after rejected update. |  | Preconditions: Tester is authenticated; valid and inactive reference values exist. Data: Numeric-like, wrong-case, whitespace, unknown and inactive codes. Expected: Every invalid value is rejected and stored valid state remains unchanged. Actual / postcondition: Passed across invalid create, update and draft checks. ¦ Rejected inputs are not persisted. |  | DonHV | 2026-07-23T10:59:07+07:00 |  | Passed | Command: npm run qa:idts41:programmatic Evidence: scripts/qa/test-idts41-code-list-validation.js Defects / limit: IDTS-32 ¦ UI value-state presentation not rerun.
FT-AUTHZ-001 | Only Tester or PM can start a bug draft — Developer / Tester / PM Req: SRS-FR-AUTH-002, SRS-FR-BUG-001 Steps: 1) Call root draft NEW as Developer. ¦ 2) Repeat as Tester. ¦ 3) Repeat as PM. |  | Preconditions: Seeded users for all three roles. Data: Root draft NEW request per role. Expected: Developer receives 403; Tester and PM are allowed. Actual / postcondition: Passed for all three role checks. ¦ Unauthorized draft does not exist. |  | DonHV | 2026-07-23T10:59:07+07:00 |  | Passed | Command: npm run qa:idts41:programmatic Evidence: scripts/qa/test-idts41-code-list-validation.js Defects / limit: IDTS-41 ¦ No fresh button-visibility browser check.
FT-AUTH-SESSION-001 | Authentication, bearer session and logout boundary — Anonymous / authenticated user Req: SRS-FR-AUTH-001, SRS-FR-AUTH-002 Steps: 1) Run npm run qa:auth:programmatic. ¦ 2) Review the 28 login, rejection, session, bearer, me, logout, revocation and sanitization checks. ¦ 3) Confirm exit code 0 and no failed/skipped check. |  | Preconditions: Local CAP service with seeded identities; no production identity provider. Data: Seeded valid, invalid and revoked-session inputs; raw transient token values are excluded from artifacts. Expected: All 28 local authentication/session checks pass; failures are sanitized and revoked sessions cannot be reused. Actual / postcondition: 28 passed, 0 failed, 0 skipped; exit code 0. ¦ Test sessions are revoked or remain only in the in-memory database. |  | DonHV | 2026-07-23T10:58:30+07:00 |  | Passed | Command: npm run qa:auth:programmatic Evidence: scripts/qa/test-auth-foundation-programmatic.js Defects / limit: IDTS-35, IDTS-52, IDTS-53 ¦ No current browser login/profile UAT and no production identity-provider claim.
FT-DUP-001 | Duplicate-checking support before create — Tester Req: SRS-FR-BUG-003 Steps: 1) Open Create Bug. ¦ 2) Run similar-bug check. ¦ 3) Review candidates and ignore the suggestion. ¦ 4) Confirm no new DuplicateLinks row and continue create. |  | Preconditions: Authenticated Tester; at least one similar and one unrelated bug. Data: A new login-failure description and classification context. Expected: Relevant candidates are shown as advice; ignoring them does not mutate data or block create. Actual / postcondition: Passed on Render Shared QA. The API and Fiori dialog returned review-only duplicate guidance, covered the no-result state, and did not mutate Bug workflow data. ¦ No automatic duplicate relation exists. |  | IDTS-100 automated acceptance under DonHV | 2026-07-24T20:42:48+07:00 |  | Passed | Command: node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses Evidence: docs/pm/evidence/idts-100/shared-qa-ai/render-ai-smoke.json, docs/pm/evidence/idts-100/shared-qa-ai-browser/all-review-actions/shared-qa-ai-browser.json Defects / limit: None ¦ Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately.
FT-CLASS-ASSIGN-001 | Classify and assign by active responsibility — Tester Req: SRS-FR-CLASS-001, SRS-FR-CLASS-004, SRS-FR-ASSIGN-001 Steps: 1) Open Create Bug. ¦ 2) Select Application Component and Defect Category. ¦ 3) Open Smart Assign/Assignee candidates. ¦ 4) Select the suitable Developer and save. ¦ 5) Reload the bug. |  | Preconditions: Active classification pairs and Developer Responsibilities exist. Data: Application Component=Bug Management; Defect Category=Fiori/UI5; one suitable and one unsuitable Developer. Expected: Only responsible active candidates are selectable; saved bug is Assigned and ownership persists after reload. Actual / postcondition: Passed on Render Shared QA. Active classification mapping was accepted, an eligible Developer was assigned, direct Developer self-assignment was denied, and the manual Smart Assign review remained available. ¦ Assigned Developer is the technical owner. |  | IDTS-100 automated acceptance under DonHV | 2026-07-24T20:42:48+07:00 |  | Passed | Command: node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json, docs/pm/evidence/idts-100/shared-qa-ai-browser/assignment/idts72-ai-browser-smoke.json Defects / limit: IDTS-56 ¦ Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately.
FT-PENDING-001 | Create without an assignee — Tester Req: SRS-FR-ASSIGN-003, SRS-FR-STATUS-009 Steps: 1) Create a valid bug. ¦ 2) Leave assignee unselected. ¦ 3) Submit and reload. ¦ 4) Inspect status and Current Action Owner. |  | Preconditions: Tester is authenticated and all required bug fields are valid. Data: Valid bug with no selected assignee. Expected: Bug is Pending Assignment; no Developer is selected automatically; PM/Tester queue owns the next action. Actual / postcondition: Passed on Render Shared QA. Activating a valid draft without an assignee produced PENDING_ASSIGNMENT, no assignee, and PM as the next processing role. ¦ Bug awaits explicit assignment. |  | IDTS-100 automated acceptance under DonHV | 2026-07-24T20:42:48+07:00 |  | Passed | Command: node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json Defects / limit: None ¦ Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately.
FT-REASSIGN-001 | Reassign with history — Tester / PM Req: SRS-FR-ASSIGN-004, SRS-FR-AUDIT-001 Steps: 1) Open the assigned bug. ¦ 2) Choose another suitable Developer. ¦ 3) Save with reassignment reason. ¦ 4) Reload ownership and History. |  | Preconditions: Assigned bug and a second suitable Developer exist. Data: Reason: workload balancing. Expected: Exactly one assignee remains; history names actor, old/new owner, reason and timestamp. Actual / postcondition: Passed on Render Shared QA. The bug moved through rejection to Pending Assignment, cleared the assignee, was reassigned, and retained exact history action types. ¦ New Developer is technical owner. |  | IDTS-100 automated acceptance under DonHV | 2026-07-24T20:42:48+07:00 |  | Passed | Command: node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json Defects / limit: None ¦ Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately.
FT-DEV-INFO-001 | Developer review and Request More Information — Developer Req: SRS-FR-STATUS-001, SRS-FR-STATUS-002, SRS-FR-STATUS-009 Steps: 1) Open as non-assigned Developer and try the action. ¦ 2) Open as assigned Developer and submit blank reason. ¦ 3) Submit the valid reason. ¦ 4) Reload status, owner, notification and history. |  | Preconditions: Assigned bug; assigned and non-assigned Developer accounts. Data: Reason: missing browser version and exact reproduction step. Expected: Wrong role/owner and blank reason are blocked; valid action sets Need More Information and Tester action ownership with audit/notification. Actual / postcondition: Passed on Render Shared QA. The assigned Developer requested more information, a blank reason returned 400, and the Tester resubmitted the bug to the same Developer. ¦ Tester must provide information and resubmit. |  | IDTS-100 automated acceptance under DonHV | 2026-07-24T20:42:48+07:00 |  | Passed | Command: node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json, docs/pm/evidence/idts-100/shared-qa-email-brevo-20260724.md Defects / limit: None ¦ Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately.
FT-REJECT-001 | Reject, correct and reassign — Developer / Tester Req: SRS-FR-STATUS-003, SRS-FR-STATUS-004, SRS-FR-STATUS-009 Steps: 1) Reject without reason and confirm validation. ¦ 2) Reject with the specific reason. ¦ 3) Reload status/history/current owner. ¦ 4) As Tester, correct classification and reassign or choose Pending Assignment. ¦ 5) Reload again. |  | Preconditions: Assigned bug with unsuitable classification or owner. Data: Reason: component is Notification, not Dashboard. Expected: Blank reason is blocked; valid rejection records follow-up; correction leaves Rejected through Assigned or Pending Assignment, never directly Need More Information. Actual / postcondition: Passed on Render Shared QA. The assigned Developer rejected with a reason; PM returned the bug to the assignment queue and completed correction follow-up by reassigning it. ¦ Bug has a clear next technical/queue owner. |  | IDTS-100 automated acceptance under DonHV | 2026-07-24T20:42:48+07:00 |  | Passed | Command: node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json, docs/pm/evidence/idts-100/shared-qa-email-brevo-20260724.md Defects / limit: None ¦ Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately.
FT-LIFECYCLE-001 | Resolve, retest, close and reopen — Developer / Tester / PM Req: SRS-FR-STATUS-005, SRS-FR-STATUS-006, SRS-FR-STATUS-007, SRS-FR-STATUS-008 Steps: 1) Developer resolves with note. ¦ 2) Tester/PM moves to Retest Required. ¦ 3) Record passing retest and close; reload. ¦ 4) On a second bug, record failing retest and reopen; reload. |  | Preconditions: Bug is In Progress and reproducible. Data: Resolution note plus one passing and one failing retest observation. Expected: Pass reaches Closed; fail reaches Reopened; required notes, owners and audit remain consistent after reload. Actual / postcondition: Passed on Render Shared QA across PM, Tester and Developer sessions: assign, review, progress, information request, resubmit, resolve, retest, close, reopen, reject and reassign all persisted with exact history and notification side effects. ¦ Closed has no next processor; Reopened returns to active handling. |  | IDTS-100 automated acceptance under DonHV | 2026-07-24T20:42:48+07:00 |  | Passed | Command: node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json, docs/pm/evidence/idts-100/shared-qa-email-brevo-20260724.md Defects / limit: None ¦ Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately.
FT-COMMENT-001 | Add comment and retain it after reconnect — Tester Req: SRS-FR-COMMENT-001, SRS-FR-COMMENT-002 Steps: 1) Add a comment through the bound action. ¦ 2) Read the comment row. ¦ 3) Reconnect to the same SQLite file. ¦ 4) Read the row again and compare bug status. |  | Preconditions: Existing bug and file-backed test database. Data: Unique sanitized comment marker. Expected: Comment remains after reconnect and does not directly change bug status. Actual / postcondition: Passed: row created and retained after reconnect. ¦ Test database remains under ignored .tmp. |  | DonHV | 2026-07-23T10:59:13+07:00 |  | Passed | Command: npm run qa:comments-attachments:programmatic Evidence: scripts/qa/test-comments-attachments-programmatic.js Defects / limit: IDTS-55 ¦ No fresh Fiori visual comment evidence.
FT-ATTACH-001 | Upload, download, reload and delete an attachment — Tester Req: SRS-DATA-007, SRS-FR-AUDIT-001 Steps: 1) Edit the root draft and upload allowed evidence. ¦ 2) Activate and reload. ¦ 3) Download and compare content. ¦ 4) Try invalid MIME/size variants. ¦ 5) Delete and verify metadata/object/history cleanup. |  | Preconditions: Authenticated Tester, existing bug and allowed small evidence file. Data: Small text/image file, disallowed MIME variant and over-limit boundary file. Expected: Allowed evidence persists and downloads; invalid variants are blocked; delete cleans storage and records history. Actual / postcondition: Passed on Render Shared QA. Two files selected before save were uploaded after activation, downloaded with matching SHA-256, persisted after redeploy, and one attachment was deleted with the subsequent download returning 404. ¦ No orphan attachment remains. |  | IDTS-100 automated acceptance under DonHV | 2026-07-24T20:42:48+07:00 |  | Passed | Command: npm run qa:idts73:browser + supported OData delete verification Evidence: docs/pm/evidence/idts-100/shared-qa-attachments/idts73-create-attachments-browser.json, docs/pm/evidence/idts-100/shared-qa-attachments/delete-verification-20260724.md Defects / limit: IDTS-55 ¦ Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately.
FT-NOTIF-001 | Notification outbox success, failure, retry and rollback isolation — System / Tester Req: SRS-FR-NOTIF-001, SRS-FR-NOTIF-002, SRS-FR-DELIVERY-001 Steps: 1) Create notification/outbox rows. ¦ 2) Process success and failure variants. ¦ 3) Advance retry and process again. ¦ 4) Inspect sanitized fields and OData shape. ¦ 5) Force business rollback and confirm rows roll back. |  | Preconditions: Seeded bug and recipient; controlled fake transport. Data: Enabled, disabled, inactive-recipient, success and secret-bearing failure variants. Expected: States are PENDING/SENT/FAILED/SKIPPED as applicable; retry succeeds; provider failure does not expose secrets or corrupt workflow. Actual / postcondition: Passed with 58 assertion calls using controlled transport. ¦ Only controlled local rows existed. |  | DonHV | 2026-07-23T10:58:52+07:00 |  | Passed | Command: npm run qa:email-outbox:programmatic Evidence: scripts/qa/test-email-outbox-programmatic.js Defects / limit: None ¦ Live provider delivery was not run; local disabled delivery is SKIPPED.
FT-PM-001 | PM monitoring flags, queues and current action owner — PM Req: SRS-FR-PM-001, SRS-FR-PM-002, SRS-FR-PM-003, SRS-FR-STATUS-009 Steps: 1) Read calculated flags. ¦ 2) Filter each monitoring queue. ¦ 3) Read currentActionOwnerDisplayName with sparse selection. ¦ 4) Compare closed-bug boundary behavior. |  | Preconditions: Seeded open, closed, pending and rejected bugs. Data: BUG-0001..0004 and one closed QA bug. Expected: Twenty expected flag/filter/owner checks match; closed bug is not overdue or pending. Actual / postcondition: 20/20 passed. ¦ Read-only monitoring changed no business data. |  | DonHV | 2026-07-23T10:59:01+07:00 |  | Passed | Command: npm run qa:pm-monitoring:programmatic Evidence: scripts/qa/test-pm-monitoring-programmatic.js Defects / limit: None ¦ No fresh dashboard visual/UX check.
FT-AI-REVIEW-001 | Human reviews AI suggestion without automatic mutation — Tester / PM Req: SRS-FR-AI-002, SRS-FR-AI-003 Steps: 1) Capture bug values before suggestion. ¦ 2) Open review suggestion. ¦ 3) Ignore it and reload. ¦ 4) Repeat failure/malformed mode. ¦ 5) Confirm bug values unchanged and safe audit/feedback. |  | Preconditions: Authenticated user; AI disabled and controlled suggestion modes available. Data: Similar/classification/handoff suggestion with safe and malformed variants. Expected: Suggestion never changes assignment, classification or lifecycle automatically; normal workflow remains usable. Actual / postcondition: Passed for disabled-provider acceptance on Render Shared QA. Similar Bugs, Classification, Handoff Summary and Smart Assignment were review-only, safe, browser-visible and did not mutate workflow. Live OpenAI provider remains NOT ACCEPTED by decision. ¦ Bug remains unchanged unless an authorized user separately applies a normal action. |  | IDTS-100 automated acceptance under DonHV | 2026-07-24T20:42:48+07:00 |  | Passed | Command: node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses Evidence: docs/pm/evidence/idts-100/shared-qa-ai/render-ai-smoke.json, docs/pm/evidence/idts-100/shared-qa-ai-browser/all-review-actions/shared-qa-ai-browser.json, docs/pm/evidence/idts-100/shared-qa-ai-browser/assignment/idts72-ai-browser-smoke.json Defects / limit: IDTS-78 ¦ Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately.

## Test Result
Run ID / exact command | Observed result / limitation | Executor | Execution date | Status / counts | Evidence
REG-AUTH-20260723 npm run qa:auth:programmatic | 28 checks passed: login, safe rejection, hashed session, bearer mapping, me, logout, revocation and sanitized internal failures. Limitation: Local seeded identities only; no production identity provider claim. Raw transient token output is excluded from mentor artifacts. | DonHV | 2026-07-23T10:58:30+07:00 | PASSED P/F/S: 28/0/0 | docs/pm/evidence/idts-100/shared-qa-acceptance-summary-20260724.md
REG-EMAIL-20260723 npm run qa:email-outbox:programmatic | 58 assertion calls passed for configuration, safe templates/deep links, PENDING/SENT/FAILED/SKIPPED, retry, sanitized failure, read-only OData, uniqueness and rollback. Limitation: No live SMTP/Brevo delivery was attempted; provider success used a controlled fake transport. Local disabled delivery remains SKIPPED, not live-provider PASS. | DonHV | 2026-07-23T10:58:52+07:00 | PASSED P/F/S: 58/0/0 | docs/pm/evidence/idts-100/shared-qa-acceptance-summary-20260724.md
REG-PM-20260723 npm run qa:pm-monitoring:programmatic | 20 checks passed for overdue, pending assignment, rejected follow-up, retest queue filters and readable current action owner. Limitation: Backend calculation/filter evidence only; no fresh browser dashboard review in this run. | DonHV | 2026-07-23T10:59:01+07:00 | PASSED P/F/S: 20/0/0 | docs/pm/evidence/idts-100/shared-qa-acceptance-summary-20260724.md
REG-CATALOG-20260723 npm run qa:idts41:programmatic | 18 checks passed for valid create, invalid/blank/inactive catalogs, persistence after rejection, draft validation and create authorization. Limitation: Programmatic service evidence; no fresh Fiori form rendering review. | DonHV | 2026-07-23T10:59:07+07:00 | PASSED P/F/S: 18/0/0 | docs/pm/evidence/idts-100/shared-qa-acceptance-summary-20260724.md
REG-COMMENT-20260723 npm run qa:comments-attachments:programmatic | Comment creation passed and the same row remained after reconnecting to the SQLite file. Limitation: The command did not execute attachment upload. Attachment draft HTTP persistence/history remains NOT_RUN in this remediation. | DonHV | 2026-07-23T10:59:13+07:00 | PASSED P/F/S: 2/0/0 | docs/pm/evidence/idts-100/shared-qa-acceptance-summary-20260724.md
REG-AI-20260723 npm run qa:idts64:programmatic | 34 checks passed for disabled-by-default behavior, mock chat/structured/embedding, safe error/timeout/config handling, OpenAI request shaping and secret redaction. Limitation: No live OpenAI provider call and no full Fiori human-review flow were executed. | DonHV | 2026-07-23T10:59:19+07:00 | PASSED P/F/S: 34/0/0 | docs/pm/evidence/idts-100/shared-qa-ai/idts72-ai-acceptance.json

## Test Data Description (hidden)
Function ID | Function Name | Created/Updated by | Created date | Reviewed by | Reviewed Date
IDTS-SAP490-FUNCTIONAL | Concrete test data and environment | DonHV | 2026-07-23 | Mentor / Supervisor | Pending review
TD-01 | Local CAP/SQLite regression Local seeded users and in-memory/file SQLite as stated per case; no production environment claim. | DonHV | 2026-07-23 | Not applicable | See linked case evidence
TD-02 | Role and authorization data PM, Tester and Developer seeded identities; no credentials are embedded in the workbook. | DonHV | 2026-07-23 | Not applicable | See linked case evidence
TD-03 | Classification and assignment data Concrete component/category/developer relationships are defined inside each linked case. | DonHV | 2026-07-23 | Not applicable | See linked case evidence
TD-04 | Attachment and notification data Small safe files, comment text, notification rows and outbox records; live provider delivery may be skipped. | DonHV | 2026-07-23 | Not applicable | See linked case evidence
TD-05 | AI advisory boundary Sanitized prompt/input, mocked or disabled provider modes, mandatory human review, no automatic bug mutation. | DonHV | 2026-07-23 | Not applicable | See linked case evidence