## Cover
TEST REPORT DOCUMENT
Project Name | Issue and Defect Tracking System in SAP |  |  | Creator | DonHV
Project Code | IDTS-SAP01 |  |  | Issue Date | 2026-07-23
Document Code | IDTS-SAP01_Test Report_v0.4 |  |  | Version | 0.4
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2026-07-23 | 0.4 | Full SAP490 test pack | M | Reconciled from canonical cases and fresh exact npm runs; Pending/Prepared is not Passed. | docs/qa/test-catalog.json
Note on D10: *A: Add M: Modify D: Delete

## Test Cases
TEST CASE LIST
Project Name |  | Issue and Defect Tracking System in SAP
Project Code |  | IDTS-SAP01
Test Environment Setup Description |  | Local Node.js/CAP/SQLite; seeded roles; exact environment is recorded per case.
No | Function Name | Sheet Name | Description | Pre-Condition
1 | UT-AI-001 — AI configuration is disabled by default | Feature 1 | SRS-FR-AI-003 UNIT / PASSED | Private AI configuration is absent.
2 | UT-AI-002 — Mock chat and structured response mapping | Feature 1 | SRS-FR-AI-003 UNIT / PASSED | Mock mode is enabled.
3 | UT-AI-003 — Embedding dimensions and model mapping | Feature 1 | SRS-FR-AI-003 UNIT / PASSED | Mock embedding dimensions are configured.
4 | UT-AI-004 — Provider error and timeout are sanitized | Feature 1 | SRS-FR-AI-002, SRS-FR-AI-003 UNIT / PASSED | Controlled provider error and timeout modes are available.
5 | UT-AI-005 — Secret redactor masks representative keys | Feature 1 | SRS-FR-AI-003 UNIT / PASSED | Redactor is loaded.
6 | FT-CREATE-001 — Create a valid bug through the service | Feature 1 | SRS-FR-BUG-001, SRS-FR-CLASS-003 FUNCTIONAL_API / PASSED | Tester is authenticated; active priority, severity and environment codes exist.
7 | FT-VALID-001 — Reject invalid, blank and inactive catalog values | Feature 1 | SRS-FR-BUG-002, SRS-FR-CLASS-003, SRS-FR-STATUS-008 FUNCTIONAL_API / PASSED | Tester is authenticated; valid and inactive reference values exist.
8 | FT-AUTHZ-001 — Only Tester or PM can start a bug draft | Feature 1 | SRS-FR-AUTH-002, SRS-FR-BUG-001 FUNCTIONAL_API / PASSED | Seeded users for all three roles.
9 | FT-AUTH-SESSION-001 — Authentication, bearer session and logout boundary | Feature 1 | SRS-FR-AUTH-001, SRS-FR-AUTH-002 PROGRAMMATIC_REGRESSION / PASSED | Local CAP service with seeded identities; no production identity provider.
10 | FT-DUP-001 — Duplicate-checking support before create | Feature 1 | SRS-FR-BUG-003 FUNCTIONAL_UI_API / PASSED | Authenticated Tester; at least one similar and one unrelated bug.
11 | FT-CLASS-ASSIGN-001 — Classify and assign by active responsibility | Feature 1 | SRS-FR-CLASS-001, SRS-FR-CLASS-004, SRS-FR-ASSIGN-001 FUNCTIONAL_UI_API / PASSED | Active classification pairs and Developer Responsibilities exist.
12 | FT-PENDING-001 — Create without an assignee | Feature 1 | SRS-FR-ASSIGN-003, SRS-FR-STATUS-009 FUNCTIONAL_UI_API / PASSED | Tester is authenticated and all required bug fields are valid.
13 | FT-REASSIGN-001 — Reassign with history | Feature 1 | SRS-FR-ASSIGN-004, SRS-FR-AUDIT-001 FUNCTIONAL_UI_API / PASSED | Assigned bug and a second suitable Developer exist.
14 | FT-DEV-INFO-001 — Developer review and Request More Information | Feature 1 | SRS-FR-STATUS-001, SRS-FR-STATUS-002, SRS-FR-STATUS-009 FUNCTIONAL_UI_API / PASSED | Assigned bug; assigned and non-assigned Developer accounts.
15 | FT-REJECT-001 — Reject, correct and reassign | Feature 1 | SRS-FR-STATUS-003, SRS-FR-STATUS-004, SRS-FR-STATUS-009 FUNCTIONAL_UI_API / PASSED | Assigned bug with unsuitable classification or owner.
16 | FT-LIFECYCLE-001 — Resolve, retest, close and reopen | Feature 1 | SRS-FR-STATUS-005, SRS-FR-STATUS-006, SRS-FR-STATUS-007, SRS-FR-STATUS-008 FUNCTIONAL_UI_API / PASSED | Bug is In Progress and reproducible.
17 | FT-COMMENT-001 — Add comment and retain it after reconnect | Feature 1 | SRS-FR-COMMENT-001, SRS-FR-COMMENT-002 FUNCTIONAL_API / PASSED | Existing bug and file-backed test database.
18 | FT-ATTACH-001 — Upload, download, reload and delete an attachment | Feature 1 | SRS-DATA-007, SRS-FR-AUDIT-001 FUNCTIONAL_HTTP_UI / PASSED | Authenticated Tester, existing bug and allowed small evidence file.
19 | FT-NOTIF-001 — Notification outbox success, failure, retry and rollback isolation | Feature 1 | SRS-FR-NOTIF-001, SRS-FR-NOTIF-002, SRS-FR-DELIVERY-001 FUNCTIONAL_INTEGRATION / PASSED | Seeded bug and recipient; controlled fake transport.
20 | FT-PM-001 — PM monitoring flags, queues and current action owner | Feature 1 | SRS-FR-PM-001, SRS-FR-PM-002, SRS-FR-PM-003, SRS-FR-STATUS-009 FUNCTIONAL_API / PASSED | Seeded open, closed, pending and rejected bugs.
21 | FT-AI-REVIEW-001 — Human reviews AI suggestion without automatic mutation | Feature 1 | SRS-FR-AI-002, SRS-FR-AI-003 FUNCTIONAL_UI_API / PASSED | Authenticated user; AI disabled and controlled suggestion modes available.
22 | UAT-001 — Create and classify a bug | Feature 2 | SRS-FR-BUG-001, SRS-FR-BUG-002, SRS-FR-CLASS-003, SRS-FR-ASSIGN-003 UAT / PREPARED | Mentor/user has a Tester account and clean test data.
23 | UAT-002 — Developer review, information request and rejection | Feature 2 | SRS-FR-STATUS-001, SRS-FR-STATUS-002, SRS-FR-STATUS-003, SRS-FR-STATUS-004 UAT / PREPARED | One suitable and one unsuitable assigned bug.
24 | UAT-003 — Resolve, retest, close and reopen | Feature 2 | SRS-FR-STATUS-005, SRS-FR-STATUS-006, SRS-FR-STATUS-007 UAT / PREPARED | Two bugs are In Progress.
25 | UAT-004 — Comments and attachment evidence | Feature 2 | SRS-FR-COMMENT-001, SRS-DATA-007, SRS-FR-AUDIT-001 UAT / PREPARED | Existing bug and allowed small file.
26 | UAT-005 — PM monitoring and action ownership | Feature 2 | SRS-FR-PM-001, SRS-FR-PM-002, SRS-FR-PM-003 UAT / PREPARED | Representative bugs exist in each monitored state.
27 | UAT-006 — Advisory AI and safe fallback | Feature 2 | SRS-FR-AI-002, SRS-FR-AI-003 UAT / PREPARED | Controlled suggestion and disabled/failure modes are available.

## Test Statistics
TEST STATISTICS
Project Name | Issue and Defect Tracking System in SAP |  | DonHV
Project Code | IDTS-SAP01 |  | Mentor / Supervisor
Document Code | IDTS-SAP01_Test Report_v0.4 |  | Issue Date |  |  | 2026-07-23
Notes | 27 planned; 21 executed; 21 passed; 0 failed; 0 blocked; 6 Not Run/Prepared. Pending is not Passed.
No | Module code | Passed | Failed | Pending | Blocked | Number of test cases
1 | Executed unit/API/integration verification | 21 | 0 | 0 | 0 | 21
2 | Manual functional and UAT preparation | 0 | 0 | 6 | 0 | 6
| Sub total | 21 | 0 | 6 | 0 | 27
| Case execution rate |  | 77.78%
| Pass rate over executed cases |  | 100%
Metric | Value | Calculation / scope
Planned cases | 27 | 27 canonical cases
Executed cases | 21 | 21 Passed + 0 Failed
Passed | 21 | Fresh evidence and required execution metadata
Failed | 0 | Executed failed outcomes
Blocked | 0 | Execution blockers
Not Run / Pending | 6 | 0 NOT_RUN + 6 PREPARED
Planned requirement traceability | 100% | 32 / 32
Executed requirement coverage | 100% | 32 / 32
Automated assertion/check count | 160 | Fresh suite-reported checks; skipped checks are not Pass
Defect count | 12 | Real tracked defects; no synthetic defect

## Feature 1
Executed unit/API/integration verification | Executed unit/API/integration verification | [13 empty] | Passed
Test requirement | Freshly executed cases with exact command or direct execution evidence. | [13 empty] | Failed
Number of TCs | 21 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | Blocked | [10 empty] | N/A
Round 1 | 21 | 0 | 0 | 0
Round 2 | 21 | 0 | 0 | 0
Round 3 | 21 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Cases
UT-AI-001 | AI configuration is disabled by default | Req: SRS-FR-AI-003 ¦ Role: N/A — module test ¦ Data: Default configuration object. ¦ 1) Load AI configuration. ¦ 2) Call chat through the wrapper. ¦ 3) Inspect success/status and sanitized result. | enabled=false; result is AI_DISABLED; no exception or unsafe diagnostic. | Private AI configuration is absent. | Passed | 2026-07-23T10:59:19+07:00 | DonHV | N/A |  |  | N/A |  |  | Actual: Passed in REG-AI-20260723. ¦ Evidence: scripts/qa/test-idts64-ai-provider.js ¦ Defects: None ¦ Limitations: No live provider. ¦ Postcondition: No business data changed.
UT-AI-002 | Mock chat and structured response mapping | Req: SRS-FR-AI-003 ¦ Role: N/A — module test ¦ Data: Safe text and ClassificationSuggestion schema. ¦ 1) Configure mock provider. ¦ 2) Call chat and structured operations. ¦ 3) Compare mapped model, text and schema. | Both operations succeed and excluded source secrets stay absent. | Mock mode is enabled. | Passed | 2026-07-23T10:59:19+07:00 | DonHV | N/A |  |  | N/A |  |  | Actual: Passed in REG-AI-20260723. ¦ Evidence: scripts/qa/test-idts64-ai-provider.js ¦ Defects: None ¦ Limitations: Deterministic mock only. ¦ Postcondition: No business data changed.
UT-AI-003 | Embedding dimensions and model mapping | Req: SRS-FR-AI-003 ¦ Role: N/A — module test ¦ Data: Six-dimensional mock vector. ¦ 1) Configure dimension=6. ¦ 2) Request an embedding. ¦ 3) Compare dimensions, vector length and model alias. | Success with exactly six values and the embedding-specific model alias. | Mock embedding dimensions are configured. | Passed | 2026-07-23T10:59:19+07:00 | DonHV | N/A |  |  | N/A |  |  | Actual: Passed in REG-AI-20260723. ¦ Evidence: scripts/qa/test-idts64-ai-provider.js ¦ Defects: None ¦ Limitations: Mock vector, not semantic-quality evaluation. ¦ Postcondition: No business data changed.
UT-AI-004 | Provider error and timeout are sanitized | Req: SRS-FR-AI-002, SRS-FR-AI-003 ¦ Role: N/A — module test ¦ Data: MOCK_PROVIDER_ERROR and delayed embedding. ¦ 1) Trigger provider error. ¦ 2) Trigger timeout. ¦ 3) Inspect retryable flags and public diagnostic text. | AI_PROVIDER_ERROR/AI_TIMEOUT are safe and retryability is preserved. | Controlled provider error and timeout modes are available. | Passed | 2026-07-23T10:59:19+07:00 | DonHV | N/A |  |  | N/A |  |  | Actual: Passed in REG-AI-20260723. ¦ Evidence: scripts/qa/test-idts64-ai-provider.js ¦ Defects: None ¦ Limitations: Controlled failure only. ¦ Postcondition: Normal non-AI workflow remains untouched.
UT-AI-005 | Secret redactor masks representative keys | Req: SRS-FR-AI-003 ¦ Role: N/A — module test ¦ Data: Synthetic AWS access key and Brevo API key patterns. ¦ 1) Pass synthetic key-shaped strings to the redactor. ¦ 2) Inspect returned text. | Both representative secrets are masked. | Redactor is loaded. | Passed | 2026-07-23T10:59:19+07:00 | DonHV | N/A |  |  | N/A |  |  | Actual: Passed in REG-AI-20260723. ¦ Evidence: scripts/qa/test-idts64-ai-provider.js ¦ Defects: None ¦ Limitations: Representative patterns only; not proof against every possible secret format. ¦ Postcondition: Synthetic data discarded.
FT-CREATE-001 | Create a valid bug through the service | Req: SRS-FR-BUG-001, SRS-FR-CLASS-003 ¦ Role: Tester ¦ Data: Complete sanitized bug payload with active codes. ¦ 1) Submit a valid create request. ¦ 2) Read the created bug by ID. ¦ 3) Check required business values. | Create succeeds and the bug is persisted with valid values. | Tester is authenticated; active priority, severity and environment codes exist. | Passed | 2026-07-23T10:59:07+07:00 | DonHV | N/A |  |  | N/A |  |  | Actual: Passed: valid active catalog codes created a bug. ¦ Evidence: scripts/qa/test-idts41-code-list-validation.js ¦ Defects: IDTS-32 ¦ Limitations: No fresh Fiori UI or reload evidence. ¦ Postcondition: Created test data remains only in the in-memory database.
FT-VALID-001 | Reject invalid, blank and inactive catalog values | Req: SRS-FR-BUG-002, SRS-FR-CLASS-003, SRS-FR-STATUS-008 ¦ Role: Tester ¦ Data: Numeric-like, wrong-case, whitespace, unknown and inactive codes. ¦ 1) Submit each invalid create/update/draft variant. ¦ 2) Check 400 response and target field. ¦ 3) Reload persisted row after rejected update. | Every invalid value is rejected and stored valid state remains unchanged. | Tester is authenticated; valid and inactive reference values exist. | Passed | 2026-07-23T10:59:07+07:00 | DonHV | N/A |  |  | N/A |  |  | Actual: Passed across invalid create, update and draft checks. ¦ Evidence: scripts/qa/test-idts41-code-list-validation.js ¦ Defects: IDTS-32 ¦ Limitations: UI value-state presentation not rerun. ¦ Postcondition: Rejected inputs are not persisted.
FT-AUTHZ-001 | Only Tester or PM can start a bug draft | Req: SRS-FR-AUTH-002, SRS-FR-BUG-001 ¦ Role: Developer / Tester / PM ¦ Data: Root draft NEW request per role. ¦ 1) Call root draft NEW as Developer. ¦ 2) Repeat as Tester. ¦ 3) Repeat as PM. | Developer receives 403; Tester and PM are allowed. | Seeded users for all three roles. | Passed | 2026-07-23T10:59:07+07:00 | DonHV | N/A |  |  | N/A |  |  | Actual: Passed for all three role checks. ¦ Evidence: scripts/qa/test-idts41-code-list-validation.js ¦ Defects: IDTS-41 ¦ Limitations: No fresh button-visibility browser check. ¦ Postcondition: Unauthorized draft does not exist.
FT-AUTH-SESSION-001 | Authentication, bearer session and logout boundary | Req: SRS-FR-AUTH-001, SRS-FR-AUTH-002 ¦ Role: Anonymous / authenticated user ¦ Data: Seeded valid, invalid and revoked-session inputs; raw transient token values are excluded from artifacts. ¦ 1) Run npm run qa:auth:programmatic. ¦ 2) Review the 28 login, rejection, session, bearer, me, logout, revocation and sanitization checks. ¦ 3) Confirm exit code 0 and no failed/skipped check. | All 28 local authentication/session checks pass; failures are sanitized and revoked sessions cannot be reused. | Local CAP service with seeded identities; no production identity provider. | Passed | 2026-07-23T10:58:30+07:00 | DonHV | N/A |  |  | N/A |  |  | Actual: 28 passed, 0 failed, 0 skipped; exit code 0. ¦ Evidence: scripts/qa/test-auth-foundation-programmatic.js ¦ Defects: IDTS-35, IDTS-52, IDTS-53 ¦ Limitations: No current browser login/profile UAT and no production identity-provider claim. ¦ Postcondition: Test sessions are revoked or remain only in the in-memory database.
FT-DUP-001 | Duplicate-checking support before create | Req: SRS-FR-BUG-003 ¦ Role: Tester ¦ Data: A new login-failure description and classification context. ¦ 1) Open Create Bug. ¦ 2) Run similar-bug check. ¦ 3) Review candidates and ignore the suggestion. ¦ 4) Confirm no new DuplicateLinks row and continue create. | Relevant candidates are shown as advice; ignoring them does not mutate data or block create. | Authenticated Tester; at least one similar and one unrelated bug. | Passed | 2026-07-24T20:42:48+07:00 | IDTS-100 automated acceptance under DonHV | N/A |  |  | N/A |  |  | Actual: Passed on Render Shared QA. The API and Fiori dialog returned review-only duplicate guidance, covered the no-result state, and did not mutate Bug workflow data. ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-ai/render-ai-smoke.json, docs/pm/evidence/idts-100/shared-qa-ai-browser/all-review-actions/shared-qa-ai-browser.json ¦ Defects: None ¦ Limitations: Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. ¦ Postcondition: No automatic duplicate relation exists.
FT-CLASS-ASSIGN-001 | Classify and assign by active responsibility | Req: SRS-FR-CLASS-001, SRS-FR-CLASS-004, SRS-FR-ASSIGN-001 ¦ Role: Tester ¦ Data: Application Component=Bug Management; Defect Category=Fiori/UI5; one suitable and one unsuitable Developer. ¦ 1) Open Create Bug. ¦ 2) Select Application Component and Defect Category. ¦ 3) Open Smart Assign/Assignee candidates. ¦ 4) Select the suitable Developer and save. ¦ 5) Reload the bug. | Only responsible active candidates are selectable; saved bug is Assigned and ownership persists after reload. | Active classification pairs and Developer Responsibilities exist. | Passed | 2026-07-24T20:42:48+07:00 | IDTS-100 automated acceptance under DonHV | N/A |  |  | N/A |  |  | Actual: Passed on Render Shared QA. Active classification mapping was accepted, an eligible Developer was assigned, direct Developer self-assignment was denied, and the manual Smart Assign review remained available. ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json, docs/pm/evidence/idts-100/shared-qa-ai-browser/assignment/idts72-ai-browser-smoke.json ¦ Defects: IDTS-56 ¦ Limitations: Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. ¦ Postcondition: Assigned Developer is the technical owner.
FT-PENDING-001 | Create without an assignee | Req: SRS-FR-ASSIGN-003, SRS-FR-STATUS-009 ¦ Role: Tester ¦ Data: Valid bug with no selected assignee. ¦ 1) Create a valid bug. ¦ 2) Leave assignee unselected. ¦ 3) Submit and reload. ¦ 4) Inspect status and Current Action Owner. | Bug is Pending Assignment; no Developer is selected automatically; PM/Tester queue owns the next action. | Tester is authenticated and all required bug fields are valid. | Passed | 2026-07-24T20:42:48+07:00 | IDTS-100 automated acceptance under DonHV | N/A |  |  | N/A |  |  | Actual: Passed on Render Shared QA. Activating a valid draft without an assignee produced PENDING_ASSIGNMENT, no assignee, and PM as the next processing role. ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json ¦ Defects: None ¦ Limitations: Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. ¦ Postcondition: Bug awaits explicit assignment.
FT-REASSIGN-001 | Reassign with history | Req: SRS-FR-ASSIGN-004, SRS-FR-AUDIT-001 ¦ Role: Tester / PM ¦ Data: Reason: workload balancing. ¦ 1) Open the assigned bug. ¦ 2) Choose another suitable Developer. ¦ 3) Save with reassignment reason. ¦ 4) Reload ownership and History. | Exactly one assignee remains; history names actor, old/new owner, reason and timestamp. | Assigned bug and a second suitable Developer exist. | Passed | 2026-07-24T20:42:48+07:00 | IDTS-100 automated acceptance under DonHV | N/A |  |  | N/A |  |  | Actual: Passed on Render Shared QA. The bug moved through rejection to Pending Assignment, cleared the assignee, was reassigned, and retained exact history action types. ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json ¦ Defects: None ¦ Limitations: Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. ¦ Postcondition: New Developer is technical owner.
FT-DEV-INFO-001 | Developer review and Request More Information | Req: SRS-FR-STATUS-001, SRS-FR-STATUS-002, SRS-FR-STATUS-009 ¦ Role: Developer ¦ Data: Reason: missing browser version and exact reproduction step. ¦ 1) Open as non-assigned Developer and try the action. ¦ 2) Open as assigned Developer and submit blank reason. ¦ 3) Submit the valid reason. ¦ 4) Reload status, owner, notification and history. | Wrong role/owner and blank reason are blocked; valid action sets Need More Information and Tester action ownership with audit/notification. | Assigned bug; assigned and non-assigned Developer accounts. | Passed | 2026-07-24T20:42:48+07:00 | IDTS-100 automated acceptance under DonHV | N/A |  |  | N/A |  |  | Actual: Passed on Render Shared QA. The assigned Developer requested more information, a blank reason returned 400, and the Tester resubmitted the bug to the same Developer. ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json, docs/pm/evidence/idts-100/shared-qa-email-brevo-20260724.md ¦ Defects: None ¦ Limitations: Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. ¦ Postcondition: Tester must provide information and resubmit.
FT-REJECT-001 | Reject, correct and reassign | Req: SRS-FR-STATUS-003, SRS-FR-STATUS-004, SRS-FR-STATUS-009 ¦ Role: Developer / Tester ¦ Data: Reason: component is Notification, not Dashboard. ¦ 1) Reject without reason and confirm validation. ¦ 2) Reject with the specific reason. ¦ 3) Reload status/history/current owner. ¦ 4) As Tester, correct classification and reassign or choose Pending Assignment. ¦ 5) Reload again. | Blank reason is blocked; valid rejection records follow-up; correction leaves Rejected through Assigned or Pending Assignment, never directly Need More Information. | Assigned bug with unsuitable classification or owner. | Passed | 2026-07-24T20:42:48+07:00 | IDTS-100 automated acceptance under DonHV | N/A |  |  | N/A |  |  | Actual: Passed on Render Shared QA. The assigned Developer rejected with a reason; PM returned the bug to the assignment queue and completed correction follow-up by reassigning it. ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json, docs/pm/evidence/idts-100/shared-qa-email-brevo-20260724.md ¦ Defects: None ¦ Limitations: Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. ¦ Postcondition: Bug has a clear next technical/queue owner.
FT-LIFECYCLE-001 | Resolve, retest, close and reopen | Req: SRS-FR-STATUS-005, SRS-FR-STATUS-006, SRS-FR-STATUS-007, SRS-FR-STATUS-008 ¦ Role: Developer / Tester / PM ¦ Data: Resolution note plus one passing and one failing retest observation. ¦ 1) Developer resolves with note. ¦ 2) Tester/PM moves to Retest Required. ¦ 3) Record passing retest and close; reload. ¦ 4) On a second bug, record failing retest and reopen; reload. | Pass reaches Closed; fail reaches Reopened; required notes, owners and audit remain consistent after reload. | Bug is In Progress and reproducible. | Passed | 2026-07-24T20:42:48+07:00 | IDTS-100 automated acceptance under DonHV | N/A |  |  | N/A |  |  | Actual: Passed on Render Shared QA across PM, Tester and Developer sessions: assign, review, progress, information request, resubmit, resolve, retest, close, reopen, reject and reassign all persisted with exact history and notification side effects. ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json, docs/pm/evidence/idts-100/shared-qa-email-brevo-20260724.md ¦ Defects: None ¦ Limitations: Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. ¦ Postcondition: Closed has no next processor; Reopened returns to active handling.
FT-COMMENT-001 | Add comment and retain it after reconnect | Req: SRS-FR-COMMENT-001, SRS-FR-COMMENT-002 ¦ Role: Tester ¦ Data: Unique sanitized comment marker. ¦ 1) Add a comment through the bound action. ¦ 2) Read the comment row. ¦ 3) Reconnect to the same SQLite file. ¦ 4) Read the row again and compare bug status. | Comment remains after reconnect and does not directly change bug status. | Existing bug and file-backed test database. | Passed | 2026-07-23T10:59:13+07:00 | DonHV | N/A |  |  | N/A |  |  | Actual: Passed: row created and retained after reconnect. ¦ Evidence: scripts/qa/test-comments-attachments-programmatic.js ¦ Defects: IDTS-55 ¦ Limitations: No fresh Fiori visual comment evidence. ¦ Postcondition: Test database remains under ignored .tmp.
FT-ATTACH-001 | Upload, download, reload and delete an attachment | Req: SRS-DATA-007, SRS-FR-AUDIT-001 ¦ Role: Tester ¦ Data: Small text/image file, disallowed MIME variant and over-limit boundary file. ¦ 1) Edit the root draft and upload allowed evidence. ¦ 2) Activate and reload. ¦ 3) Download and compare content. ¦ 4) Try invalid MIME/size variants. ¦ 5) Delete and verify metadata/object/history cleanup. | Allowed evidence persists and downloads; invalid variants are blocked; delete cleans storage and records history. | Authenticated Tester, existing bug and allowed small evidence file. | Passed | 2026-07-24T20:42:48+07:00 | IDTS-100 automated acceptance under DonHV | N/A |  |  | N/A |  |  | Actual: Passed on Render Shared QA. Two files selected before save were uploaded after activation, downloaded with matching SHA-256, persisted after redeploy, and one attachment was deleted with the subsequent download returning 404. ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-attachments/idts73-create-attachments-browser.json, docs/pm/evidence/idts-100/shared-qa-attachments/delete-verification-20260724.md ¦ Defects: IDTS-55 ¦ Limitations: Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. ¦ Postcondition: No orphan attachment remains.
FT-NOTIF-001 | Notification outbox success, failure, retry and rollback isolation | Req: SRS-FR-NOTIF-001, SRS-FR-NOTIF-002, SRS-FR-DELIVERY-001 ¦ Role: System / Tester ¦ Data: Enabled, disabled, inactive-recipient, success and secret-bearing failure variants. ¦ 1) Create notification/outbox rows. ¦ 2) Process success and failure variants. ¦ 3) Advance retry and process again. ¦ 4) Inspect sanitized fields and OData shape. ¦ 5) Force business rollback and confirm rows roll back. | States are PENDING/SENT/FAILED/SKIPPED as applicable; retry succeeds; provider failure does not expose secrets or corrupt workflow. | Seeded bug and recipient; controlled fake transport. | Passed | 2026-07-23T10:58:52+07:00 | DonHV | N/A |  |  | N/A |  |  | Actual: Passed with 58 assertion calls using controlled transport. ¦ Evidence: scripts/qa/test-email-outbox-programmatic.js ¦ Defects: None ¦ Limitations: Live provider delivery was not run; local disabled delivery is SKIPPED. ¦ Postcondition: Only controlled local rows existed.
FT-PM-001 | PM monitoring flags, queues and current action owner | Req: SRS-FR-PM-001, SRS-FR-PM-002, SRS-FR-PM-003, SRS-FR-STATUS-009 ¦ Role: PM ¦ Data: BUG-0001..0004 and one closed QA bug. ¦ 1) Read calculated flags. ¦ 2) Filter each monitoring queue. ¦ 3) Read currentActionOwnerDisplayName with sparse selection. ¦ 4) Compare closed-bug boundary behavior. | Twenty expected flag/filter/owner checks match; closed bug is not overdue or pending. | Seeded open, closed, pending and rejected bugs. | Passed | 2026-07-23T10:59:01+07:00 | DonHV | N/A |  |  | N/A |  |  | Actual: 20/20 passed. ¦ Evidence: scripts/qa/test-pm-monitoring-programmatic.js ¦ Defects: None ¦ Limitations: No fresh dashboard visual/UX check. ¦ Postcondition: Read-only monitoring changed no business data.
FT-AI-REVIEW-001 | Human reviews AI suggestion without automatic mutation | Req: SRS-FR-AI-002, SRS-FR-AI-003 ¦ Role: Tester / PM ¦ Data: Similar/classification/handoff suggestion with safe and malformed variants. ¦ 1) Capture bug values before suggestion. ¦ 2) Open review suggestion. ¦ 3) Ignore it and reload. ¦ 4) Repeat failure/malformed mode. ¦ 5) Confirm bug values unchanged and safe audit/feedback. | Suggestion never changes assignment, classification or lifecycle automatically; normal workflow remains usable. | Authenticated user; AI disabled and controlled suggestion modes available. | Passed | 2026-07-24T20:42:48+07:00 | IDTS-100 automated acceptance under DonHV | N/A |  |  | N/A |  |  | Actual: Passed for disabled-provider acceptance on Render Shared QA. Similar Bugs, Classification, Handoff Summary and Smart Assignment were review-only, safe, browser-visible and did not mutate workflow. Live OpenAI provider remains NOT ACCEPTED by decision. ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-ai/render-ai-smoke.json, docs/pm/evidence/idts-100/shared-qa-ai-browser/all-review-actions/shared-qa-ai-browser.json, docs/pm/evidence/idts-100/shared-qa-ai-browser/assignment/idts72-ai-browser-smoke.json ¦ Defects: IDTS-78 ¦ Limitations: Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. ¦ Postcondition: Bug remains unchanged unless an authorized user separately applies a normal action.
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Feature 2
Manual functional and UAT preparation
Feature | Manual functional and UAT preparation | [13 empty] | Passed
Test requirement | Manual UI flows remain NOT_RUN and UAT remains PREPARED; no sign-off claim. | [13 empty] | Failed
Number of TCs | 6 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | Blocked | [10 empty] | N/A
Round 1 | 0 | 0 | 6 | 0
Round 2 | 0 | 0 | 6 | 0
Round 3 | 0 | 0 | 6 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Cases
UAT-001 | Create and classify a bug | Req: SRS-FR-BUG-001, SRS-FR-BUG-002, SRS-FR-CLASS-003, SRS-FR-ASSIGN-003 ¦ Role: Tester ¦ Data: UI issue in Bug Management; valid priority/severity; no assignee for the Pending variant. ¦ 1) Open Create Bug. ¦ 2) Enter all required data. ¦ 3) Select classification. ¦ 4) Submit once with an assignee and once without. ¦ 5) Reload both bugs. | Assigned/Pending Assignment match the explicit choice; no automatic Developer selection; data persists. | Mentor/user has a Tester account and clean test data. | Pending |  |  | N/A |  |  | N/A |  |  | Actual: Not run ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json, docs/pm/evidence/idts-100/shared-qa-attachments/idts73-create-attachments-browser.json ¦ Defects: None ¦ Limitations: PREPARED ? human execution, decision, date and signature remain required. ¦ Postcondition: Created UAT bugs are labelled for cleanup.
UAT-002 | Developer review, information request and rejection | Req: SRS-FR-STATUS-001, SRS-FR-STATUS-002, SRS-FR-STATUS-003, SRS-FR-STATUS-004 ¦ Role: Developer / Tester ¦ Data: Specific missing-information reason and rejection reason. ¦ 1) As assigned Developer, review both bugs. ¦ 2) Request information on one with reason. ¦ 3) Reject the other with reason. ¦ 4) As Tester, resubmit/correct and reassign. ¦ 5) Reload history and ownership. | Required reasons, allowed transitions, notifications, history and Current Action Owner are correct. | One suitable and one unsuitable assigned bug. | Pending |  |  | N/A |  |  | N/A |  |  | Actual: Not run ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json, docs/pm/evidence/idts-100/shared-qa-email-brevo-20260724.md ¦ Defects: None ¦ Limitations: PREPARED ? human execution, decision, date and signature remain required. ¦ Postcondition: Both bugs have clear next owners.
UAT-003 | Resolve, retest, close and reopen | Req: SRS-FR-STATUS-005, SRS-FR-STATUS-006, SRS-FR-STATUS-007 ¦ Role: Developer / Tester / PM ¦ Data: Resolution notes plus one pass and one fail observation. ¦ 1) Resolve both bugs. ¦ 2) Move both to Retest Required. ¦ 3) Close the passing bug. ¦ 4) Reopen the failing bug. ¦ 5) Reload status/history/owners. | Pass closes; fail reopens; no unsupported post-retest information-request branch appears. | Two bugs are In Progress. | Pending |  |  | N/A |  |  | N/A |  |  | Actual: Not run ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json, docs/pm/evidence/idts-100/shared-qa-email-brevo-20260724.md ¦ Defects: None ¦ Limitations: PREPARED ? human execution, decision, date and signature remain required. ¦ Postcondition: One Closed and one Reopened UAT bug.
UAT-004 | Comments and attachment evidence | Req: SRS-FR-COMMENT-001, SRS-DATA-007, SRS-FR-AUDIT-001 ¦ Role: Tester / Developer ¦ Data: Specific comment and a sanitized evidence file. ¦ 1) Add a comment. ¦ 2) Upload evidence through edit/draft. ¦ 3) Save and reload. ¦ 4) Download and compare. ¦ 5) Delete and confirm cleanup/history. | Comment and evidence persist; download works; cleanup and history are correct. | Existing bug and allowed small file. | Pending |  |  | N/A |  |  | N/A |  |  | Actual: Not run ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-attachments/idts73-create-attachments-browser.json, docs/pm/evidence/idts-100/shared-qa-attachments/delete-verification-20260724.md ¦ Defects: None ¦ Limitations: PREPARED ? human execution, decision, date and signature remain required. ¦ Postcondition: Attachment cleanup follows the UAT plan.
UAT-005 | PM monitoring and action ownership | Req: SRS-FR-PM-001, SRS-FR-PM-002, SRS-FR-PM-003 ¦ Role: PM ¦ Data: Pending, overdue, rejected, retest, closed and assigned bugs. ¦ 1) Open PM monitoring views. ¦ 2) Apply each queue/filter. ¦ 3) Compare counts to source bugs. ¦ 4) Open representative rows and inspect owners. ¦ 5) Reload the dashboard. | Counts, filters and owner wording are understandable and remain consistent after reload. | Representative bugs exist in each monitored state. | Pending |  |  | N/A |  |  | N/A |  |  | Actual: Not run ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json, docs/pm/evidence/idts-100/local-fast/ ¦ Defects: None ¦ Limitations: PREPARED ? human execution, decision, date and signature remain required. ¦ Postcondition: Monitoring remains read-only.
UAT-006 | Advisory AI and safe fallback | Req: SRS-FR-AI-002, SRS-FR-AI-003 ¦ Role: Tester / PM ¦ Data: Similar/classification/handoff suggestion on a test bug. ¦ 1) Record bug values. ¦ 2) Open and ignore a suggestion. ¦ 3) Reload and compare values. ¦ 4) Trigger disabled/failure mode. ¦ 5) Continue a normal authorized bug action. | No automatic mutation; safe message is shown; normal action remains available. | Controlled suggestion and disabled/failure modes are available. | Pending |  |  | N/A |  |  | N/A |  |  | Actual: Not run ¦ Evidence: docs/pm/evidence/idts-100/shared-qa-ai/render-ai-smoke.json, docs/pm/evidence/idts-100/shared-qa-ai-browser/all-review-actions/shared-qa-ai-browser.json, docs/pm/evidence/idts-100/shared-qa-ai-browser/assignment/idts72-ai-browser-smoke.json ¦ Defects: None ¦ Limitations: PREPARED ? human execution, decision, date and signature remain required. ¦ Postcondition: Test bug remains under human control.
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case