## Cover
CONFIGURATION WORKBOOK
| Code | IDTS-SAP01
| Version | 0.5
| Effective Date | 2026-07-25

## Record of change
RECORD OF CHANGE
No | Effective Date | Version | Change Description | Reason | Reviewer | Approver
1 | 2026-06-21 | 0.1 | Initial configuration baseline | Document local CAP/SQLite setup | Mentor / Supervisor | Pending
2 | 2026-07-02 | 0.2 | Shared QA configuration | Add Render, PostgreSQL, S3 and Brevo controls | Mentor / Supervisor | Pending
3 | 2026-07-24 | 0.3 | Security and AI controls | Clarify private configuration and disabled live OpenAI | Mentor / Supervisor | Pending
4 | 2026-07-25 | 0.4 | Official-template remediation | Align five official sheets with deployed CAP/Fiori baseline | Mentor / Supervisor | Pending
5 | 2026-07-25 | 0.5 | Runtime trace and formal-layout correction | Add exact location, verification, rollback and evidence controls | Mentor / Supervisor | Pending

## Checklist
Configuration Checklist
Module | Sequence | Sheet name | Configuration Items | Tcode | Status | Comments
IDTS | 1 | Authentication | All ¦ srv/auth.js; srv/auth/custom-auth.js; /odata/v4/auth/ | Required; session duration from private CAP config | DonHV ¦ Verify: Login/me/logout + anonymous 401 + sanitized error evidence | Rollback/evidence: Revoke sessions or roll back runtime deploy
IDTS | 2 | BugService | All ¦ srv/service.cds; srv/service.js; /odata/v4/bug/ | Required; no private default | DonHV ¦ Verify: Metadata/compile, role and lifecycle regression | Rollback/evidence: Roll back runtime deploy
IDTS | 3 | CAP profiles | Local/QA ¦ package.json and private environment | SQLite local; PostgreSQL QA; HANA direction undecided | DonHV ¦ Verify: Resolve profile and database binding without printing URL | Rollback/evidence: Restore prior private profile/binding
IDTS | 4 | PostgreSQL | Shared QA ¦ Render database binding | Required for shared QA; no credential in workbook | DonHV ¦ Verify: Persistence/readback after restart; 21 PASSED + 6 UAT PREPARED truth | Rollback/evidence: Backup/readback then restore or migrate
IDTS | 5 | SQLite | Local ¦ db.sqlite generated locally | Default local-only development store | Each developer ¦ Verify: cds deploy local + focused tests | Rollback/evidence: Regenerate local database from approved seed
IDTS | 6 | AWS S3 | Shared QA ¦ private attachment binding | Required for live attachment binary; no key stored here | DonHV ¦ Verify: Upload/download/SHA-256/reload/delete evidence | Rollback/evidence: Disable binding and use approved local fallback only outside QA
IDTS | 7 | Email provider | Shared QA ¦ private Brevo/SMTP configuration | Optional delivery channel; workflow remains independent | DonHV ¦ Verify: NotificationDeliveries PENDING→SENT and inbox evidence | Rollback/evidence: Disable email; preserve in-app notification/outbox rows
IDTS | 8 | Render | Shared QA ¦ service settings/deploy control | Manual deploy; pre-deploy remains safe; no broad seed reload | DonHV ¦ Verify: Frozen commit/deploy ID, health 200, protected 401, authenticated smoke | Rollback/evidence: Roll back to prior live deploy
IDTS | 9 | AI | All ¦ private AI config and srv/ai provider seam | Disabled by default; live OpenAI NOT ACCEPTED | DonHV ¦ Verify: 25/25 disabled-provider/fallback/no-mutation evidence | Rollback/evidence: Keep disabled; normal workflow remains available
IDTS | 10 | Security | All ¦ private environment and repository gates | Mandatory; no secret/private value in source or evidence | All members ¦ Verify: Secret scan, safe error and role-boundary tests | Rollback/evidence: Revoke exposed value and rotate credential
IDTS | 11 | Migration | Shared QA ¦ additive migration helper | Required only for schema change; idempotent | DonHV ¦ Verify: Dry-run, backup, run twice, schema/data readback | Rollback/evidence: Transaction rollback or restore backup
IDTS | 12 | Health check | Shared QA ¦ /odata/v4/auth/$metadata and protected OData | Required before acceptance | DonHV/NhanT ¦ Verify: Metadata 200; anonymous 401; authenticated 200; no 5xx | Rollback/evidence: Stop acceptance and roll back deploy
IDTS | 13 | Developer dataset | Shared QA ¦ Users and DeveloperResponsibilities | 14 users: 12 Developers; 30 responsibilities | DonHV ¦ Verify: Count/readback plus smart-assignment smoke | Rollback/evidence: Restore database backup; do not broad-seed reload
Security note: this workbook documents keys and locations only. It never stores credentials, tokens, private endpoints, database URLs or personal data.

## 4 (hidden)
Customizing Guide |  | Release | System | Category | Created by | Date
[5 empty] | Revised by | Date
[5 empty] | Reviewed by | Date
IDTS CAP/Fiori configuration control
No credentials, tokens, private endpoint or personal data are stored in this artifact.
N/A — Not applicable to SAP CAP/Fiori implementation. IDTS does not use classic SAP customizing transactions or T-codes. Equivalent runtime configuration uses CAP profiles and private environment variables.

## 5 (hidden)
Customizing Guide |  | Release | System | Category | Created by | Date
[5 empty] | Revised by | Date
[5 empty] | Reviewed by | Date
IDTS CAP/Fiori configuration control
No credentials, tokens, private endpoint or personal data are stored in this artifact.
N/A — This is not an SAP Transport Request. IDTS uses Git branches, reviewed pull requests, additive database migration and controlled Render deployment.