## Cover
TEST REPORT DOCUMENT
Project Name | Issue and Defect Tracking System in SAP |  |  | Creator | DonHV
Project Code | IDTS-SAP01 |  |  | Issue Date | 2026-06-18
Document Code |  |  |  | Version | 0.1
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
<Date when these changes are effective> | 2026-06-18 | 0.1 |  | Sprint 02 retest report covering create, lifecycle, comments, attachments, history, and notifications. | Retest matrix and SAP490 generated artifacts
Note on D10: *A: Add M: Modify D: Delete

## Test Cases
TEST CASE LIST
Project Name |  | Issue and Defect Tracking System in SAP
Project Code |  | IDTS-SAP01
Test Environment Setup Description |  | Local CAP SQLite server, mock users, browser + shell QA, and draft attachment flow.
No | Function Name | Sheet Name | Description | Pre-Condition
1 | Sprint 02 Create and Assignment | Feature 1 | Create flow, assignment, developer lifecycle, and status validation | Current Sprint 02 CAP/Fiori baseline
2 | Sprint 02 Collaboration and Audit | Feature 2 | Comments, attachments, grouped history, notifications, and follow-up transitions | Current Sprint 02 CAP/Fiori baseline
3 | Function C | Feature1
4 | Function D | Feature2
5 | Function E | Feature2

## Test Statistics
TEST STATISTICS
Project Name | Issue and Defect Tracking System in SAP |  | DonHV
Project Code | IDTS-SAP01 |  | DonHV / Team
Document Code |  |  | Issue Date |  |  | 2026-06-18
Notes | Release includes happy-flow retest for create, assignment, developer processing, comments, attachments, history, and notifications.
No | Module code | Passed | Failed | Pending | N/A | Number of test cases
1
2
Sub total
| Test coverage |  |  | %
| Test successful coverage |  |  | %

## Feature 1
Feature | Sprint 02 Create and Lifecycle | [13 empty] | Passed
Test requirement | Create bug, assignment, developer review, progress, request more information, reject, resolve, retest, close, and reopen. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Function A
SC-01a | Create a bug with all mandatory fields and no assignee. | Valid title, description, reproduction details, component, category, priority, severity. | Create succeeds and persisted status becomes PENDING_ASSIGNMENT. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV | Pending
SC-01b | Create a bug without title. | All mandatory fields except title. | Request is rejected with HTTP 400 and title-required validation. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV | Pending
SC-02a | Create a bug with a valid assignee selected. | Valid developer profile mapped to selected component/category. | Create succeeds and persisted status becomes ASSIGNED. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV | Pending
SC-05a | Assign BUG-0001 to a valid developer. | Valid assignee ID and assignment note. | Action succeeds, status becomes ASSIGNED, and notification is created. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-05b | Assign a bug without assigneeID. | Assignment note only. | Request is rejected with HTTP 400. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV | Pending
SC-06a | Move an assigned bug to IN_REVIEW. | Assigned bug and optional note. | Action succeeds and status becomes IN_REVIEW. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV | Pending
SC-07a | Move an in-review bug to IN_PROGRESS. | Bug in IN_REVIEW status. | Action succeeds and status becomes IN_PROGRESS. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-08a | Request more information with a reason. | Reason: Need clearer reproduction evidence. | Action succeeds and status becomes NEED_MORE_INFORMATION. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV | Pending
SC-08b | Request more information without a reason. | Empty reason. | Request is rejected with HTTP 400. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-08c | Resubmit a bug from NEED_MORE_INFORMATION back to the developer path. | Follow-up text plus existing bug in NEED_MORE_INFORMATION state. | Action succeeds, status becomes ASSIGNED, and developer follow-up is re-opened. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-09a | Reject a bug with a classification reason. | Reason: Wrong component/category mapping. | Action succeeds and status becomes REJECTED. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-09b | Reject a bug without a reason. | Empty reason. | Request is rejected with HTTP 400. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-10a | Move a rejected bug to PENDING_ASSIGNMENT. | Rejected bug plus follow-up note. | Action succeeds, assignee is cleared, and status becomes PENDING_ASSIGNMENT. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-11a | Resolve an in-progress bug with a developer note. | Resolve note describing the technical fix. | Action succeeds and status becomes RESOLVED. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-11b | Resolve an in-progress bug without a developer note. | Empty resolve note. | Request is rejected with HTTP 400. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-12a | Send a resolved bug to RETEST_REQUIRED. | Resolved bug plus tester-facing note. | Action succeeds and status becomes RETEST_REQUIRED. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-12b | Close a resolved bug when QA decides no separate retest cycle is needed. | Bug in RESOLVED state. | Action succeeds and status becomes CLOSED. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-13a | Reopen a bug with a reason. | Reason: issue still reproducible. | Action succeeds and status becomes REOPENED. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-13b | Reopen a bug without a reason. | Empty reason. | Request is rejected with HTTP 400. | Valid seed/demo state | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case

## Feature 2
Feature | Sprint 02 Collaboration and Audit | [13 empty] | Passed
Test requirement | Comment, draft attachment upload/download, grouped history, and notification verification. | [13 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Function D
SC-03a | Create draft attachment metadata from the draft Object Page. | Draft bug context plus file name, media type, and file size. | Attachment metadata row is created successfully in draft mode. | Local CAP + HTTP endpoints | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV | Pending
SC-03b | Upload binary content for a draft attachment. | Real text file content through OData media stream endpoint. | Upload succeeds and content is available after draft activation and download. | Local CAP + HTTP endpoints | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV | Pending
SC-04a | Add a comment to an active bug. | Comment text submitted by Tester/Developer/PM. | Comment row is created with business-friendly author display. | Local CAP + HTTP endpoints | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV | Pending
SC-04b | Verify comment history entry after addComment. | Latest HistoryLogs / HistoryEvents after addComment. | History captures the comment event with readable field/value information. | Local CAP + HTTP endpoints | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
SC-08d | Verify resubmit writes a comment and a developer notification. | Latest comments and notifications after resubmitToDeveloper. | A readable follow-up comment and developer notification both exist. | Local CAP + HTTP endpoints | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV | Pending
SC-14a | Verify grouped history for assignment/status/comment/attachment changes. | HistoryEvents and HistoryLogs after full lifecycle and draft attachment flow. | Audit trail exists and shows readable actor, field, and value information. | Local CAP + HTTP endpoints | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV | Pending
SC-14b | Verify notifications after assignment and follow-up transitions. | Notifications list for assignment/reject/request-info flow. | Notification rows exist with business-readable recipient and event names. | Local CAP + HTTP endpoints | Passed | 2026-06-18 | DonHV | Passed | 2026-06-18 | DonHV
Note on E10: List all test cases (must run before this case), conditions that must be done, or required state that the system should be in before performing this case