## Evidence Index
Evidence ID / Mã bằng chứng | Case ID / Mã ca | Run ID | Command / Lệnh | Baseline commit | Deploy ID / SHA | Environment / executor / time | Result / Kết quả | Actual result / Kết quả thực tế | Limitation / Giới hạn | Evidence artifact / Bằng chứng | Source or test at baseline / Nguồn hoặc test
EVD-UT-AI-001 | UT-AI-001 | REG-AI-20260723 | npm run qa:idts64:programmatic | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Local Node.js module test ¦ DonHV ¦ 2026-07-23T10:59:19+07:00 | PASSED ¦ P/F/S 34/0/0 ¦ exit 0 | Passed in REG-AI-20260723. | No live provider. | docs/pm/evidence/idts-100/shared-qa-ai/idts72-ai-acceptance.json | scripts/qa/test-idts64-ai-provider.js
EVD-UT-AI-002 | UT-AI-002 | REG-AI-20260723 | npm run qa:idts64:programmatic | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Local Node.js module test ¦ DonHV ¦ 2026-07-23T10:59:19+07:00 | PASSED ¦ P/F/S 34/0/0 ¦ exit 0 | Passed in REG-AI-20260723. | Deterministic mock only. | docs/pm/evidence/idts-100/shared-qa-ai/idts72-ai-acceptance.json | scripts/qa/test-idts64-ai-provider.js
EVD-UT-AI-003 | UT-AI-003 | REG-AI-20260723 | npm run qa:idts64:programmatic | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Local Node.js module test ¦ DonHV ¦ 2026-07-23T10:59:19+07:00 | PASSED ¦ P/F/S 34/0/0 ¦ exit 0 | Passed in REG-AI-20260723. | Mock vector, not semantic-quality evaluation. | docs/pm/evidence/idts-100/shared-qa-ai/idts72-ai-acceptance.json | scripts/qa/test-idts64-ai-provider.js
EVD-UT-AI-004 | UT-AI-004 | REG-AI-20260723 | npm run qa:idts64:programmatic | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Local Node.js module test ¦ DonHV ¦ 2026-07-23T10:59:19+07:00 | PASSED ¦ P/F/S 34/0/0 ¦ exit 0 | Passed in REG-AI-20260723. | Controlled failure only. | docs/pm/evidence/idts-100/shared-qa-ai/idts72-ai-acceptance.json | scripts/qa/test-idts64-ai-provider.js
EVD-UT-AI-005 | UT-AI-005 | REG-AI-20260723 | npm run qa:idts64:programmatic | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Local Node.js module test ¦ DonHV ¦ 2026-07-23T10:59:19+07:00 | PASSED ¦ P/F/S 34/0/0 ¦ exit 0 | Passed in REG-AI-20260723. | Representative patterns only; not proof against every possible secret format. | docs/pm/evidence/idts-100/shared-qa-ai/idts72-ai-acceptance.json | scripts/qa/test-idts64-ai-provider.js
EVD-FT-CREATE-001 | FT-CREATE-001 | REG-CATALOG-20260723 | npm run qa:idts41:programmatic | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Local CAP service; in-memory SQLite ¦ DonHV ¦ 2026-07-23T10:59:07+07:00 | PASSED ¦ P/F/S 18/0/0 ¦ exit 0 | Passed: valid active catalog codes created a bug. | No fresh Fiori UI or reload evidence. | docs/pm/evidence/idts-100/shared-qa-acceptance-summary-20260724.md | scripts/qa/test-idts41-code-list-validation.js
EVD-FT-VALID-001 | FT-VALID-001 | REG-CATALOG-20260723 | npm run qa:idts41:programmatic | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Local CAP service; in-memory SQLite ¦ DonHV ¦ 2026-07-23T10:59:07+07:00 | PASSED ¦ P/F/S 18/0/0 ¦ exit 0 | Passed across invalid create, update and draft checks. | UI value-state presentation not rerun. | docs/pm/evidence/idts-100/shared-qa-acceptance-summary-20260724.md | scripts/qa/test-idts41-code-list-validation.js
EVD-FT-AUTHZ-001 | FT-AUTHZ-001 | REG-CATALOG-20260723 | npm run qa:idts41:programmatic | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Local CAP service; in-memory SQLite ¦ DonHV ¦ 2026-07-23T10:59:07+07:00 | PASSED ¦ P/F/S 18/0/0 ¦ exit 0 | Passed for all three role checks. | No fresh button-visibility browser check. | docs/pm/evidence/idts-100/shared-qa-acceptance-summary-20260724.md | scripts/qa/test-idts41-code-list-validation.js
EVD-FT-AUTH-SESSION-001 | FT-AUTH-SESSION-001 | REG-AUTH-20260723 | npm run qa:auth:programmatic | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Local Node.js; CAP; in-memory SQLite ¦ DonHV ¦ 2026-07-23T10:58:30+07:00 | PASSED ¦ P/F/S 28/0/0 ¦ exit 0 | 28 passed, 0 failed, 0 skipped; exit code 0. | No current browser login/profile UAT and no production identity-provider claim. | docs/pm/evidence/idts-100/shared-qa-acceptance-summary-20260724.md | scripts/qa/test-auth-foundation-programmatic.js
EVD-FT-DUP-001 | FT-DUP-001 | SHARED-QA-20260724 | node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Render Shared QA ¦ IDTS-100 automated acceptance under DonHV ¦ 2026-07-24T20:42:48+07:00 | PASSED | Passed on Render Shared QA. The API and Fiori dialog returned review-only duplicate guidance, covered the no-result state, and did not mutate Bug workflow data. | Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. | docs/pm/evidence/idts-100/shared-qa-ai/render-ai-smoke.json | N/A — manual or artifact-based verification
EVD-FT-CLASS-ASSIGN-001 | FT-CLASS-ASSIGN-001 | SHARED-QA-20260724 | node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Render Shared QA ¦ IDTS-100 automated acceptance under DonHV ¦ 2026-07-24T20:42:48+07:00 | PASSED | Passed on Render Shared QA. Active classification mapping was accepted, an eligible Developer was assigned, direct Developer self-assignment was denied, and the manual Smart Assign review remained available. | Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. | docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json | N/A — manual or artifact-based verification
EVD-FT-PENDING-001 | FT-PENDING-001 | SHARED-QA-20260724 | node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Render Shared QA ¦ IDTS-100 automated acceptance under DonHV ¦ 2026-07-24T20:42:48+07:00 | PASSED | Passed on Render Shared QA. Activating a valid draft without an assignee produced PENDING_ASSIGNMENT, no assignee, and PM as the next processing role. | Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. | docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json | N/A — manual or artifact-based verification
EVD-FT-REASSIGN-001 | FT-REASSIGN-001 | SHARED-QA-20260724 | node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Render Shared QA ¦ IDTS-100 automated acceptance under DonHV ¦ 2026-07-24T20:42:48+07:00 | PASSED | Passed on Render Shared QA. The bug moved through rejection to Pending Assignment, cleared the assignee, was reassigned, and retained exact history action types. | Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. | docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json | N/A — manual or artifact-based verification
EVD-FT-DEV-INFO-001 | FT-DEV-INFO-001 | SHARED-QA-20260724 | node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Render Shared QA ¦ IDTS-100 automated acceptance under DonHV ¦ 2026-07-24T20:42:48+07:00 | PASSED | Passed on Render Shared QA. The assigned Developer requested more information, a blank reason returned 400, and the Tester resubmitted the bug to the same Developer. | Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. | docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json | N/A — manual or artifact-based verification
EVD-FT-REJECT-001 | FT-REJECT-001 | SHARED-QA-20260724 | node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Render Shared QA ¦ IDTS-100 automated acceptance under DonHV ¦ 2026-07-24T20:42:48+07:00 | PASSED | Passed on Render Shared QA. The assigned Developer rejected with a reason; PM returned the bug to the assignment queue and completed correction follow-up by reassigning it. | Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. | docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json | N/A — manual or artifact-based verification
EVD-FT-LIFECYCLE-001 | FT-LIFECYCLE-001 | SHARED-QA-20260724 | node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Render Shared QA ¦ IDTS-100 automated acceptance under DonHV ¦ 2026-07-24T20:42:48+07:00 | PASSED | Passed on Render Shared QA across PM, Tester and Developer sessions: assign, review, progress, information request, resubmit, resolve, retest, close, reopen, reject and reassign all persisted with exact history and notification side effects. | Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. | docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json | N/A — manual or artifact-based verification
EVD-FT-COMMENT-001 | FT-COMMENT-001 | REG-COMMENT-20260723 | npm run qa:comments-attachments:programmatic | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Local CAP; file-backed SQLite ¦ DonHV ¦ 2026-07-23T10:59:13+07:00 | PASSED ¦ P/F/S 2/0/0 ¦ exit 0 | Passed: row created and retained after reconnect. | No fresh Fiori visual comment evidence. | docs/pm/evidence/idts-100/shared-qa-acceptance-summary-20260724.md | scripts/qa/test-comments-attachments-programmatic.js
EVD-FT-ATTACH-001 | FT-ATTACH-001 | SHARED-QA-20260724 | npm run qa:idts73:browser + supported OData delete verification | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Render Shared QA ¦ IDTS-100 automated acceptance under DonHV ¦ 2026-07-24T20:42:48+07:00 | PASSED | Passed on Render Shared QA. Two files selected before save were uploaded after activation, downloaded with matching SHA-256, persisted after redeploy, and one attachment was deleted with the subsequent download returning 404. | Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. | docs/pm/evidence/idts-100/shared-qa-attachments/idts73-create-attachments-browser.json | N/A — manual or artifact-based verification
EVD-FT-NOTIF-001 | FT-NOTIF-001 | REG-EMAIL-20260723 | npm run qa:email-outbox:programmatic | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Local CAP; in-memory SQLite; fake transport ¦ DonHV ¦ 2026-07-23T10:58:52+07:00 | PASSED ¦ P/F/S 58/0/0 ¦ exit 0 | Passed with 58 assertion calls using controlled transport. | Live provider delivery was not run; local disabled delivery is SKIPPED. | docs/pm/evidence/idts-100/shared-qa-acceptance-summary-20260724.md | scripts/qa/test-email-outbox-programmatic.js
EVD-FT-PM-001 | FT-PM-001 | REG-PM-20260723 | npm run qa:pm-monitoring:programmatic | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Local CAP; in-memory SQLite ¦ DonHV ¦ 2026-07-23T10:59:01+07:00 | PASSED ¦ P/F/S 20/0/0 ¦ exit 0 | 20/20 passed. | No fresh dashboard visual/UX check. | docs/pm/evidence/idts-100/shared-qa-acceptance-summary-20260724.md | scripts/qa/test-pm-monitoring-programmatic.js
EVD-FT-AI-REVIEW-001 | FT-AI-REVIEW-001 | SHARED-QA-20260724 | node scripts/qa/test-idts100-shared-qa-lifecycle.js and focused browser/API harnesses | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Render Shared QA ¦ IDTS-100 automated acceptance under DonHV ¦ 2026-07-24T20:42:48+07:00 | PASSED | Passed for disabled-provider acceptance on Render Shared QA. Similar Bugs, Classification, Handoff Summary and Smart Assignment were review-only, safe, browser-visible and did not mutate workflow. Live OpenAI provider remains NOT ACCEPTED by decision. | Agent-executed acceptance evidence; formal human UAT sign-off is tracked separately. | docs/pm/evidence/idts-100/shared-qa-ai/render-ai-smoke.json | N/A — manual or artifact-based verification
EVD-UAT-001 | UAT-001 | UAT-NOT-EXECUTED | Manual UAT pending | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Mentor-approved UAT environment ¦ Pending human executor ¦ Not executed | PREPARED | Not executed; prepared only. | PREPARED ? human execution, decision, date and signature remain required. | docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json | N/A — manual or artifact-based verification
EVD-UAT-002 | UAT-002 | UAT-NOT-EXECUTED | Manual UAT pending | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Mentor-approved UAT environment ¦ Pending human executor ¦ Not executed | PREPARED | Not executed; prepared only. | PREPARED ? human execution, decision, date and signature remain required. | docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json | N/A — manual or artifact-based verification
EVD-UAT-003 | UAT-003 | UAT-NOT-EXECUTED | Manual UAT pending | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Mentor-approved UAT environment ¦ Pending human executor ¦ Not executed | PREPARED | Not executed; prepared only. | PREPARED ? human execution, decision, date and signature remain required. | docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json | N/A — manual or artifact-based verification
EVD-UAT-004 | UAT-004 | UAT-NOT-EXECUTED | Manual UAT pending | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Mentor-approved UAT environment ¦ Pending human executor ¦ Not executed | PREPARED | Not executed; prepared only. | PREPARED ? human execution, decision, date and signature remain required. | docs/pm/evidence/idts-100/shared-qa-attachments/idts73-create-attachments-browser.json | N/A — manual or artifact-based verification
EVD-UAT-005 | UAT-005 | UAT-NOT-EXECUTED | Manual UAT pending | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Mentor-approved UAT environment ¦ Pending human executor ¦ Not executed | PREPARED | Not executed; prepared only. | PREPARED ? human execution, decision, date and signature remain required. | docs/pm/evidence/idts-100/shared-qa-lifecycle/shared-qa-lifecycle.json | N/A — manual or artifact-based verification
EVD-UAT-006 | UAT-006 | UAT-NOT-EXECUTED | Manual UAT pending | c953cd7ad3683fc2a891ad3d09708f236f157902 | dep-d9hmfko4n6ts73b5egsg c953cd7ad3683fc2a891ad3d09708f236f157902 | Mentor-approved UAT environment ¦ Pending human executor ¦ Not executed | PREPARED | Not executed; prepared only. | PREPARED ? human execution, decision, date and signature remain required. | docs/pm/evidence/idts-100/shared-qa-ai/render-ai-smoke.json | N/A — manual or artifact-based verification