## Cover
User Acceptance Test (UAT)
| Module | IDTS | Module Name | Issue and Defect Tracking System in SAP
| Function ID | IDTS-SAP490-UAT
| Function Name | Prepared mentor/user acceptance cases
| Created Date | 2026-07-23 | Last Update Date | 2026-07-23
|  |  | Approver | Reviewer | Creator
DonHV

## Histories
No | Version | Description | Sheet | Modified date | Modified by
1 | 0.2 | Prepared executable UAT cases; actual result, defect, decision, tester, date and sign-off remain blank. | Test Scenario, Test Cases, Test Result | 2026-07-23 | DonHV

## Test Scenario
TEST SCENARIOS
No | Case ID | Persona / role | Tcode | State / limitation
1 | UAT-001 | Developer / Tester |  | Create and classify a bug | Mentor/user has a Tester account and clean test data. | UI issue in Bug Management; valid priority/severity; no assignee for the Pending variant. | Assigned/Pending Assignment match the explicit choice; no automatic Developer selection; data persists. | PREPARED — not executed; mentor/user sign-off pending
2 | UAT-002 |  |  | Developer review, information request and rejection | One suitable and one unsuitable assigned bug. | Specific missing-information reason and rejection reason. | Required reasons, allowed transitions, notifications, history and Current Action Owner are correct. | PREPARED — not executed; mentor/user sign-off pending
3 | UAT-003 | Developer / Tester / PM |  | Resolve, retest, close and reopen | Two bugs are In Progress. | Resolution notes plus one pass and one fail observation. | Pass closes; fail reopens; no unsupported post-retest information-request branch appears. | PREPARED — not executed; mentor/user sign-off pending
4 | UAT-004 | Tester / Developer |  | Comments and attachment evidence | Existing bug and allowed small file. | Specific comment and a sanitized evidence file. | Comment and evidence persist; download works; cleanup and history are correct. | PREPARED — not executed; mentor/user sign-off pending
5 | UAT-005 | PM |  | PM monitoring and action ownership | Representative bugs exist in each monitored state. | Pending, overdue, rejected, retest, closed and assigned bugs. | Counts, filters and owner wording are understandable and remain consistent after reload. | PREPARED — not executed; mentor/user sign-off pending
6 | UAT-006 | Tester / PM |  | Advisory AI and safe fallback | Controlled suggestion and disabled/failure modes are available. | Similar/classification/handoff suggestion on a test bug. | No automatic mutation; safe message is shown; normal action remains available. | PREPARED — not executed; mentor/user sign-off pending

## Test Cases
Business Flow |  | Function Name |  |  | Created/Updated by | Created date |  | Reviewed by |  | Reviewed Date
IDTS SAP490 prepared UAT |  | Mentor/user acceptance execution |  |  | DonHV | 2026-07-23 |  | Mentor / User |  | Pending execution
NO. | Test Contents | [8 empty] | Tester / Date / Sign-off
| Test Cases |  | Test Data | Predicted Test Results |  | Actual Result | Defect ID |  | Decision
UAT-001 | Create and classify a bug — Tester Req: SRS-FR-BUG-001, SRS-FR-BUG-002, SRS-FR-CLASS-003, SRS-FR-ASSIGN-003 Objective: Confirm a Tester can create a complete bug with explicit assignment choice. PREPARED — not executed; no sign-off |  | Preconditions: Mentor/user has a Tester account and clean test data. Data: UI issue in Bug Management; valid priority/severity; no assignee for the Pending variant. Steps: 1) Open Create Bug. ¦ 2) Enter all required data. ¦ 3) Select classification. ¦ 4) Submit once with an assignee and once without. ¦ 5) Reload both bugs. | Assertion / expected: Assigned/Pending Assignment match the explicit choice; no automatic Developer selection; data persists. Postcondition / persistence: Created UAT bugs are labelled for cleanup. Pass/Fail rule: Pass only when every acceptance checkpoint matches; otherwise Fail and record a defect.
UAT-002 | Developer review, information request and rejection — Developer / Tester Req: SRS-FR-STATUS-001, SRS-FR-STATUS-002, SRS-FR-STATUS-003, SRS-FR-STATUS-004 Objective: Confirm controlled Developer actions and clear follow-up ownership. PREPARED — not executed; no sign-off |  | Preconditions: One suitable and one unsuitable assigned bug. Data: Specific missing-information reason and rejection reason. Steps: 1) As assigned Developer, review both bugs. ¦ 2) Request information on one with reason. ¦ 3) Reject the other with reason. ¦ 4) As Tester, resubmit/correct and reassign. ¦ 5) Reload history and ownership. | Assertion / expected: Required reasons, allowed transitions, notifications, history and Current Action Owner are correct. Postcondition / persistence: Both bugs have clear next owners. Pass/Fail rule: Pass only when every acceptance checkpoint matches; otherwise Fail and record a defect.
UAT-003 | Resolve, retest, close and reopen — Developer / Tester / PM Req: SRS-FR-STATUS-005, SRS-FR-STATUS-006, SRS-FR-STATUS-007 Objective: Confirm accepted and failed retest outcomes. PREPARED — not executed; no sign-off |  | Preconditions: Two bugs are In Progress. Data: Resolution notes plus one pass and one fail observation. Steps: 1) Resolve both bugs. ¦ 2) Move both to Retest Required. ¦ 3) Close the passing bug. ¦ 4) Reopen the failing bug. ¦ 5) Reload status/history/owners. | Assertion / expected: Pass closes; fail reopens; no unsupported post-retest information-request branch appears. Postcondition / persistence: One Closed and one Reopened UAT bug. Pass/Fail rule: Pass only when every acceptance checkpoint matches; otherwise Fail and record a defect.
UAT-004 | Comments and attachment evidence — Tester / Developer Req: SRS-FR-COMMENT-001, SRS-DATA-007, SRS-FR-AUDIT-001 Objective: Confirm business users can collaborate and retain evidence after reload. PREPARED — not executed; no sign-off |  | Preconditions: Existing bug and allowed small file. Data: Specific comment and a sanitized evidence file. Steps: 1) Add a comment. ¦ 2) Upload evidence through edit/draft. ¦ 3) Save and reload. ¦ 4) Download and compare. ¦ 5) Delete and confirm cleanup/history. | Assertion / expected: Comment and evidence persist; download works; cleanup and history are correct. Postcondition / persistence: Attachment cleanup follows the UAT plan. Pass/Fail rule: Pass only when every acceptance checkpoint matches; otherwise Fail and record a defect.
UAT-005 | PM monitoring and action ownership — PM Req: SRS-FR-PM-001, SRS-FR-PM-002, SRS-FR-PM-003 Objective: Confirm PM can understand queues, workload, overdue and current action ownership. PREPARED — not executed; no sign-off |  | Preconditions: Representative bugs exist in each monitored state. Data: Pending, overdue, rejected, retest, closed and assigned bugs. Steps: 1) Open PM monitoring views. ¦ 2) Apply each queue/filter. ¦ 3) Compare counts to source bugs. ¦ 4) Open representative rows and inspect owners. ¦ 5) Reload the dashboard. | Assertion / expected: Counts, filters and owner wording are understandable and remain consistent after reload. Postcondition / persistence: Monitoring remains read-only. Pass/Fail rule: Pass only when every acceptance checkpoint matches; otherwise Fail and record a defect.
UAT-006 | Advisory AI and safe fallback — Tester / PM Req: SRS-FR-AI-002, SRS-FR-AI-003 Objective: Confirm suggestions require human review and failure does not block normal work. PREPARED — not executed; no sign-off |  | Preconditions: Controlled suggestion and disabled/failure modes are available. Data: Similar/classification/handoff suggestion on a test bug. Steps: 1) Record bug values. ¦ 2) Open and ignore a suggestion. ¦ 3) Reload and compare values. ¦ 4) Trigger disabled/failure mode. ¦ 5) Continue a normal authorized bug action. | Assertion / expected: No automatic mutation; safe message is shown; normal action remains available. Postcondition / persistence: Test bug remains under human control. Pass/Fail rule: Pass only when every acceptance checkpoint matches; otherwise Fail and record a defect.

## Test Result
Test Case ID | Actual Result | Defect ID | Decision | Tester / Date | Sign-off
UAT-001
UAT-002
UAT-003
UAT-004
UAT-005
UAT-006